Proposed Action and Monitoring Plan Based on the recommendations of the

Stop TB Partnership Evaluation

This document comprises a proposed action and monitoring plan according to the outcome of the meeting of the Evaluation Steering Committee and the Coordinating Board Working Committee which took place in Geneva on January 27, 2004. Action categories in the plan are:

- Procedural Changes,

- Structural Changes,

- GDF-specific actions,

- TB control

- Regional, national and sub-national partnership coordination, and

- Global partnership coordination, advocacy and resource mobilisation.

| Type of action | Assoc. recs. | Specific actions | Exec. agent | Start date and completion date | Milestones | Monitoring plan |
| --- | --- | --- | --- | --- | --- | --- |
| (1) Procedural changes and GDF specific actions | 11, 13, 85 | Financial policy for the Partnership and Secretariat including policy on exposure related to grants | PRA of the Secretariat | S: Feb 1, C: April 15, | First draft available for circulation to CB: March 1, | Ex Com to monitor based on periodic reports from Secretariat |
| (2) Procedural changes and GDF specific actions | 14, 86, 88, 8, 9 | Financial reporting system for the Partnership and Secretariat including GDF | PRA of the Secretariat | S: Feb 1, C: July 31 | Proposal for system outline available for discussion within Secretariat by May1 | Ex Sec to monitor development and implementation. Ex Com to monitor quality of output. |
| (4) Procedural changes | 28, 32, 33, 34, 35, 36,37, 38, 40, 41, 42, 45, 48, 49, 50, 61, 62, 71, 72, 73, 77-84 | Following CB decision on recs 28, 34, 36, 38, 40, 41, 42 and 45, develop a concise procedures manual for the Secretariat and Partnership | CB for decisions, followed by Consultant | S: Feb 15 C: May 1 | First draft for comments by March 30. | Ex Sec to monitor process. Manual to be subject to approval by CB. Compliance with Manual to be monitored by Ex Com. |
| (5) Structural Changes | 2, 28, 56 | CB to make decision on the optimal Board composition and composition of WGs and task forces. CB to decide on a fair and transparent process for achieving the desired composition. Secretariat to implement | Following CB decision, Secretariat, possibly WEF | S: Jan 27 C: July 31 | Identify process for identifying reps by April 30. Identify reps by July 1, full integration by July 31 | Secretariat to manage process. Ex Com to check on outcome |
| (6) Structural Changes and GDF specific actions and Global partnership coordination, advocacy and resource mobilisation | 7, 10, 26, 93 | Development of RM strategy, establishment of RM task force, determination of funding flows, implementation of strategy | Secretariat PRA, RM TF, Board members, consultant | S: on-going | As identified in RM strategy and as determined by RMTF for funding flow study | Ex Sec to supervise PRA. TF to report to CB |
| (7) Structural Changes | 18, 22, 23, 24, 25, 28, 29, 30, 31, 39, 47, 51, 53, 54, 57, 58, 63, 74, 75, 76 | CB to decide on any structural changes at New Delhi with input from the Eval SC and WC. Based on outcome, amend Basic Framework Document, including processes for the formation and dissolution of task forces and working groups. | CB to decide on any required structural changes. Consultant to make amendments. Secretariat to implement | S: April 1 C: May 30 | First draft for comments by April 30. | Basic Framework text to be subject to approval by CB. Compliance with Framework to be monitored by Ex Com. |
| (8) Structural Changes | 41, 59 | Secretariat to make a proposal on delegation of authority to the WC and Eval.SC, making use of p30 of eval text. These committees to present their proposal to the CB for decision in Delhi and possible establishment of Executive Committee | Evaluation SC and WC with support from Secretariat. CB to make final decision. | S: Jan 27 C: March 11 | Secretariat proposal to be completed by early Feb. Teleconference of ESC and WC to take place in mid Feb. | CB to provide oversight. Report to be discussed by full Board in New Delhi. |
| (9) Structural Changes | 20, 21 | Hold satellite sessions at the Partners Forum to enhance the formation of functional constituencies among NGOs, donors and new tools working groups. A post-mortem of the PF should take place at the CB meeting in October 2004 at which time decisions will be taken on the format, function and timing of future PF. Secretariat to implement outcome. | Partnership team leader, Secretariat, CB | S: Jan 27 C: October 31. | Satellite session held at partners forum March 24-25. Report findings to Board shortly thereafter. Board to conduct PF post-mortem October 2004. | Ex Com to monitor outcome |
| (10) Structural Changes and Global partnership coordination, advocacy and resource mobilisation | 27, 46, | Working Group liaison post to be established by the Secretariat, A&C strategy to embrace new tools and budget support for new tools WGs through Secretariat. | Executive Secretary and A&C working group | ongoing |  | WG chairs to monitor effectiveness |
| (11) Structural Changes, GDF specific action, and global partnership coordination, advocacy and RM | 60, 65, 67, 68, 69, 70 | Human resource strategy and restructuring of the Secretariat including GDF | Executive Secretary, HR consultant in collaboration with HTM MSU and WHO PER | S: Jan 27 C: October | Executive Secretary to determine optimal Secretariat structure | Executive Secretary to present proposed structure to the CB in Delhi, for information. |
| (12) GDF Specific Actions | 7, 12 | Improve knowledge base on justifications for using GDF, develop revised GDF strategic plan | GDF manager and consultant | S: ongoing C: October | Draft strategic plan distributed for comments by June 30 | Exec Secretary and Ex Com |
| (13) GDF Specific Actions | 89, 90 | GDF performance reporting system in place and operating | GDF manager and consultant | S: March 26 C: June 30 | First report ready for posting at the end of the second quarter, 2004 | Ex Sec and Ex Com |
| (14) TB Control | 1, 6 | Implementation of recommendations of the Second Ad Hoc Committee on the TB Epidemic | DEWG, Partners Forum, CB, A&CWG, RMTF | ongoing | ISAC project milestones, input and commitments from partners in session 5 of the Partners Forum | CB to periodically review progress. WHO to report on the status of the TB epidemic. |
| (15) TB Control and national and sub-national partnership coordination | 3 | DEWG PPM Subgroup, workplace TB control initiative of WEF, expansion of national partnerships to civil society, R&D networks | CB, DEWG, WEF, Secretariat and Regional partnerships | ongoing | According to specific project plans. | CB to periodically review progress |
| (16) TB control | 16 | Provide briefings to LFAs on TB and HIV_TB issues including technical assistance and how to assess procurement plans | WHO STB, WHO EDM, and other qualified technical partners, | S: Jan 27 C: October | Determine focal point by Feb 2, Determine possible trainers by Feb 29, reach agreement with GFATM on process and content by May 30. Begin briefings June 15 | WHO STB |
| (17) Regional, national and sub-national partnership coordination | 3, 4, 6, 56 | Further support initiatives at country level including national and sub-national partnerships, PPM, workplace guidelines, R&D networks, according to a strategic plan | Secretariat and Working Groups | S: Jan 27 C: ongoing | Strategic plan draft by May 30. Implementation to start immediately. | Ex Sec and WG chairs with periodic review by the Board. |
| (18) Regional, national and sub.national partnership coordination | 6 | Enhance liaison with other partnerships and initiatives, particularly RBM and the 3 X 5 initiative. | CB and STB Partners | S: Jan 27 C: Dec 31 for finalisation of strategy. Implementation ongoing | CB to explore options through consultation. | CB to provide oversight and periodic review. |
| (19) Global partnership coordination, advocacy and resource mobilisation | 5, 11, 17, | Accelerated Board action including liaison function with GFATM Board, and improved functioning of the constituency mechanism | Executive Secretary, A&CWG, RMTF | ongoing | As determined by Executive Secretary in consultation with the Chair. | Outcomes monitored through overall Partnership results and periodic evaluations |
| (21) Global partnership coordination, advocacy and resource mobilisation | 44, 45, 92 | Second global plan to stop TB (GPII) to include a comprehensive and cohesive vision of how the various working group streams of activity come together, and a plan for monitoring against Global Plan targets | Secretariat | S: ongoing C: Dec 31 2005 | Process for GPII agreed and WG liaison person to draft vision statement: June 30 Other milestones as in GPII process | Ex Sec and WG chairs based on agreed GP II process |
| (22) Global partnership coordination, advocacy and resource mobilisation | 55, 91 | Detailed advocacy and communications strategy developed and implemented, to include planning and production of an annual report for the Partnership to include highlights and advocacy materials | Secretariat and A&C working group, with consultant | S: April 15 C: October | Draft strategy by June 30 | Ex Sec and Ex Com |
| (23) Structural changes | 64 | The CB to issue a statement on the revision of the grade of the Executive Secretary to at least D1 in order to meet the community standard. Dir STB to follow up with DGO on this matter | CB and DIr STB | S: March 22 C: Sept | Statement to be issued from CB to WHO following the Delhi CB meeting | CB Chair and Dir STB |