## Sheet1
DOC 2.05-3.2
Secretariat Biennium Work Plan
CONTENTS
Schedule 1: Financial Summary
Schedule 2: Proposed Budget Allocation
Schedule 3: Detailed Work Plan 2006-2007

## Grand Total of Planned Costs
| Components | Total Planned Cost, US$
1 | Governance | 4273125
2 | Support to Partnerships and Working Groups | 4395184
3 | Advocacy, Communication and Social Mobilization | 4314789.36
4 | Resource Mobilization | 698010
5 | Administration and Infrastructural Support | 3158115.24
16839223.6
| Reserve for Partnership | 1000000
| Total Partnership | 17839223.6
6 | Global TB Drug Facility | 71365998
| Reserve for GDF | 1500000
| Total GDF | 72865998
| GRAND TOTAL | 90705221.6

## Budget Cost&Gap
Resources Available in US$
| Partnership | 15203296
| GDF | 68715000
| TOTAL | 83918296
| Title | Sub-total | Total Planned Cost, US$ | Budgeted Cost, US$ | Gap, US$
C1. | Governance |  | 4273125 | 4273125 | 0
| SC1. Governance | 2156040
| SC2. Executive Secretary's Office | 2117085
C2. | Support to Partnerships and Working Groups |  | 4395184 | 2059257 | 2335927
| SC1. National Partnership Building | 1124024
| SC2. Working Group Management | 3271160
C3. | Advocacy, Communication and Social Mobilization |  | 4314789.36 | 4314789.36 | 0
| SC1. Global Advocacy and SM | 1961000
| SC2. Country Level Advocacy and Communication and SM | 1765960
| SC3.TB-affected community empowerment and mobilization | 587829.36
C4. | Resource Mobilization |  | 698010 | 698010 | 0
C5. | Administration and Infrastructural Support |  | 3158115.24 | 3158115 | 0.24
| SC1. Existing Donor Relations | 159000
| SC2. Financial Management | 159000
| SC3. Personnel and General administration | 2279000
| SC4. Information Technology | 561115.24
| Sub-total Partnership |  | 16839223.6 | 14503296.36 | 2335927.24
| Reserve |  | 1000000 | 700000 | 300000
| Total Partnership |  | 17839223.6 | 15203296.36 | 2635927.24
C6. | Global TB Drug Facility |  | 71365998 | 67715000 | 3650998
| SC1. Application, Review and Monitoring | 2851612
| SC2. Procurement and Supply | 65416006
| SC3. General Management and Support | 3098380
| Reserve |  | 1500000 | 1000000 | 500000
| Total GDF |  | 72865998 | 68715000 | 4150998
| GRAND TOTAL |  | 90705221.6 | 83918296.36 | 6786925.24

## Governance (w ES office)
Stop TB Partnership Work plan 2006-2007 (Schedule 3)
Component |  | Product/Service |  | Activity | Resp. Officer | Salaries | Travel | Contractual Services | Gen. Expenses | Meeting | Publication Distribution | Direct Fin Support/ country | PSC | Total
C1. Governance |  |  |  | Total Component Cost |  | 1786250 | 400000 | 325000 | 320000 | 650000 | 50000 | 500000 | 241875 | 4273125
SC1.Governance |  |  |  | Total Cost |  | 559000 | 150000 | 125000 | 0 | 650000 | 50000 | 500000 | 122040 | 2156040
| 1 | Partners' Forum |  |  | LB | 0 | 0 | 95000 |  | 200000 | 50000 | 0 | 20700 | 365700
|  |  | 1.1 | Logistical arrangements |  | 0 | 0 | 0 |  | 200000 | 0 | 0 | 12000 | 212000
|  |  | 1.2 | Materials production |  | 0 | 0 | 0 |  | 0 | 50000 | 0 | 3000 | 53000
|  |  | 1.3 | Promotional activities |  | 0 | 0 | 45000 |  | 0 | 0 | 0 | 2700 | 47700
|  |  | 1.4 | Administrative support |  | 0 | 0 | 50000 |  | 0 | 0 | 0 | 3000 | 53000
| 2 | Coordinating Board Meetings (four meetings) |  |  | LB | 0 | 70000 | 0 |  | 300000 | 0 | 0 | 22200 | 392200
|  |  | 2.1 | Logistical arrangements |  | 0 | 0 | 0 |  | 150000 | 0 | 0 | 9000 | 159000
|  |  | 2.2 | Travel by participants |  | 0 | 0 | 0 |  | 150000 | 0 | 0 | 9000 | 159000
|  |  | 2.3 | Nominated staff participation |  | 0 | 70000 | 0 |  | 0 | 0 | 0 | 4200 | 74200
| 3 | High Level Missions (HLM) |  |  | LB | 0 | 30000 | 0 |  | 50000 | 0 | 500000 | 34800 | 614800
|  |  | 3.1 | Logistical arrangement |  | 0 | 0 | 0 |  | 50000 | 0 | 0 | 3000 | 53000
|  |  | 3.2 | Nominated staff participation |  | 0 | 30000 | 0 |  | 0 | 0 | 0 | 1800 | 31800
|  |  | 3.3 | TB acceleration seed funding in HLM countries |  | 0 | 0 | 0 |  | 0 | 0 | 500000 | 30000 | 530000
| 4 | TB Financing Summit |  |  | LB | 0 | 20000 | 0 |  | 100000 | 0 | 0 | 7200 | 127200
|  |  | 4.1 | Africa TB financing summit |  | 0 | 0 | 0 |  | 100000 | 0 | 0 | 6000 | 106000
|  |  | 4.2 | Nominated staff participation |  | 0 | 20000 | 0 |  | 0 | 0 | 0 | 1200 | 21200
| 5 | Governance activities |  |  | LB | 0 | 30000 | 30000 |  | 0 | 0 | 0 | 3600 | 63600
|  |  | 5.1 | Enhance engagement with non traditional partners |  | 0 | 0 | 15000 |  | 0 | 0 | 0 | 900 | 15900
|  |  | 5.2 | TB Champions/Leaders and External Relations |  | 0 | 25000 | 0 |  | 0 | 0 | 0 | 1500 | 26500
|  |  | 5.3 | Initiation of grant discussion with EU |  |  | 5000 | 15000 |  |  |  |  | 1200 | 21200
| 6 | Governance Staff |  |  | LB | 559000 | 0 | 0 |  | 0 | 0 | 0 | 33540 | 592540
|  |  | 6.1 | Baker Louise |  | 366000 | 0 | 0 |  | 0 | 0 | 0 | 21960 | 387960
|  |  | 6.2 | De Guman Winniefred C. |  | 193000 | 0 | 0 |  | 0 | 0 | 0 | 11580 | 204580
SC1. Executive Secretary's Office |  |  |  | Total Sub-component Cost |  | 1227250 | 250000 | 200000 | 320000 |  |  |  | 119835 | 2117085
| 1 | External Relations |  |  | ME | 0 | 200000 | 0 | 320000 | 0 | 0 | 0 | 31200 | 551200
|  |  | 1.1 | Directing the work of Stop TB Secretariat and negotiating with WHO and other partners |  | 0 | 0 | 0 | 300000 |  |  |  | 18000 | 318000
|  |  | 1.2 | Participation in High Level Mission |  | 0 | 100000 | 0 | 0 |  |  |  | 6000 | 106000
|  |  | 1.3 | Convening and participating in TBP Coordinating Board meetings |  | 0 | 20000 | 0 | 0 |  |  |  | 1200 | 21200
|  |  | 1.4 | Convening and participating in Executive Committee meetings |  | 0 | 0 | 0 | 20000 |  |  |  | 1200 | 21200
|  |  | 1.5 | Travel to meet media and for political lobbing |  | 0 | 80000 | 0 | 0 |  |  |  | 4800 | 84800
| 2 | Executive Secretary Office Staff |  |  | ME | 911500 | 0 | 0 | 0 | 0 | 0 | 0 | 54690 | 966190
|  |  | 2.1 | Espinal Fuentes Marcos |  | 479000 | 0 | 0 | 0 |  |  |  | 28740 | 507740
|  |  | 2.2 | Dolores Corazon R. |  | 222000 | 0 | 0 | 0 |  |  |  | 13320 | 235320
|  |  | 2.3 | Holger |  | 210500 | [6 empty] | 12630 | 223130
| 3 | Global Plan |  |  | DM | 315750 | 50000 | 200000 | 0 | 0 | 0 | 0 | 33945 | 599695
|  |  | 3.1 | Consultation |  |  | 50000 | 200000 |  |  |  |  | 15000 | 265000
|  |  | 3.2 | Salary Dermot |  | 315750 | [6 empty] | 18945 | 334695
Note on C7: Ababor:

## Suppor to Partn & WG
Stop TB Partnership Work plan 2006-2007 (Schedule 3)
Component |  | Product/Service | Activity | Resp. Officer | Salaries | Travel | Contractual Services | Meeting | Publication Distribution | Direct Fin Support/country | Other Exp-Grants | PSC | Total
C2. Support to Partnerships and Working Groups |  |  | Total Component Cost |  | 822000 | 0 | 448000 | 60000 | 46400 | 200000 | 2570000 | 248784 | 4395184
SC1. National Partnership Building |  |  | Total Sub-component Cost |  | 306000 | 0 | 448000 | 60000 | 46400 | 200000 | 0 | 63624 | 1124024
| 1 | Capacity and partnership building in countries and regions |  | VD | 0 | 0 | 410000 | 60000 | 46400 | 200000 | 0 | 42984 | 759384
|  | 1.1 | Tools and resources |  | 0 | 0 | 120000 | 0 | 0 | 0 |  | 7200 | 127200
|  | 1.2 | Training and support of existing partners |  | 0 | 0 | 170000 | 0 | 0 | 0 |  | 10200 | 180200
|  | 1.3 | Adoption and translation of national partnership tools and guidelines into UN languages |  | 0 | 0 | 0 | 0 | 46400 | 0 |  | 2784 | 49184
|  | 1.4 | Technical assistance and consolations |  | 0 | 0 | 120000 | 60000 | 0 | 0 |  | 10800 | 190800
|  | 1.5 | Seed funding for emerging national and regional partnership |  | 0 | 0 | 0 | 0 | 0 | 200000 |  | 12000 | 212000
| 2 | Program management |  | VD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.1 | Project management and planning |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
|  | 2.2 | Research and development of new products and tools |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 3 | Partner Outreach |  | VD | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 1680 | 29680
|  | 3.1 | Research, identification and outreach to potential new partners |  | 0 | 0 | 28000 | 0 | 0 | 0 |  | 1680 | 29680
| 4 | National Partnership Database |  | VD | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 600 | 10600
|  | 4.1 | Creation of data base for collecting analyzing and reporting on national partnerships interventions |  | 0 | 0 | 10000 | 0 | 0 | 0 |  | 600 | 10600
|  | 4.2 | Partners directory |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 5 | Task Force on TB and Poverty |  | VD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.1 | Secretariat functions, conference call administrative coordination |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
|  | 5.2 | Monitoring evaluation and research of SG work plan |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
|  | 5.3 | Report writing |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 6 | Coordination with other Working Groups |  | VD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6.1. | Meeting with other working groups |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 7 | National partnership building Staff |  | VD | 306000 | 0 | 0 | 0 | 0 | 0 | 0 | 18360 | 324360
|  | 7.1 | Diaz Valerie |  | 306000 | 0 | 0 | 0 | 0 | 0 |  | 18360 | 324360
SC2. Working Group Management |  |  | Total Sub-component Cost | SE | 516000 | 0 | 0 | 0 | 0 | 0 | 2570000 | 185160 | 3271160
| 1 | TB Vaccine |  | Uli Fruth | [6 empty] | 350000 | 21000 | 371000
|  | 1.1 | Meetings | [7 empty] | 175000 | 10500 | 185500
|  | 1.2 | Consultants | [7 empty] | 87500 | 5250 | 92750
|  | 1.3 | Capacity building | [7 empty] | 52500 | 3150 | 55650
|  | 1.4 | Advocacy/Pub/Web | [7 empty] | 35000 | 2100 | 37100
| 2 | TB Drug |  | Maria Freire/Heather | [6 empty] | 200000 | 12000 | 212000
|  | 2.1 | Meetings | [7 empty] | 120000 | 7200 | 127200
|  | 2.2 | Advocacy/web/Publications | [7 empty] | 20000 | 1200 | 21200
|  | 2.3 | Impact studies | [7 empty] | 60000 | 3600 | 63600
| 3 | TB Diagnostics |  | Giorgio/Jane | [6 empty] | 220000 | 13200 | 233200
|  | 3.1 | Meetings | [7 empty] | 140000 | 8400 | 148400
|  | 3.2 | Advocacy/Web/Publications | [7 empty] | 20000 | 1200 | 21200
|  | 3.3 | Consultancy | [7 empty] | 60000 | 3600 | 63600
| 4 | DOTS Expansion |  | Leo Blanc | [6 empty] | 1200000 | 72000 | 1272000
|  | 4.1 | Meeting | [7 empty] | 840000 | 50400 | 890400
|  | 4.2 | Monitoring | [7 empty] | 80000 | 4800 | 84800
|  | 4.3 | Coordination process | [7 empty] | 80000 | 4800 | 84800
|  | 4.4 | Training of consultant | [7 empty] | 80000 | 4800 | 84800
|  | 4.5 | Advocacy, Web, Pub | [7 empty] | 120000 | 7200 | 127200
| 5 | TB/HIV |  | Paul Nunn | [6 empty] | 300000 | 18000 | 318000
|  | 5.1 | Meetings
|  | 5.2 | Publications
|  | 5.3 | Staff/A&C
| 6 | DOTS Plus |  | Kitty Lambrecht | [6 empty] | 300000 | 18000 | 318000
|  | 6.1 | Meetings
|  | 6.2 | Publications
|  | 6.3 | Staff/consultants
| 7 | Working Group Management Staff |  |  | 516000 | 0 | 0 | 0 | 0 | 0 | 0 | 30960 | 546960
|  | 7.1 | Sara England |  | 366000 | [6 empty] | 21960 | 387960
|  | 7.2 | Rachel Bauquerez |  | 150000 | [6 empty] | 9000 | 159000
0

## ACSM part1
Stop TB Partnership Work plan (Schedule 3)
Component |  | Product/Service |  | Activity | Resp. Officer | Salaries | Travel | Contractual Services | Meeting | Publication Distribution | PSC | Total
C3. Advocacy, Communication and Social Mobilisation (ACSM)
|  |  |  | Total Component Cost |  | 1648556 | 380000 | 1260000 | 627000 | 155000 | 244233.36 | 4314789.36
SC1. Global Advocacy and SM |  |  |  | Total Sub-component Cost |  | 910000 | 155000 | 425000 | 240000 | 120000 | 111000 | 1961000
| 1 | World TB Day (WTBD) |  |  | ML | 0 | 20000 | 60000 | 0 | 30000 | 6600 | 116600
|  |  | 1.1 | WTBD work plan and theme |  | 0 | 10000 | 0 | 0 | 0 | 600 | 10600
|  |  | 1.2 | Printing & distribution of WTBD materials |  | 0 | 0 | 0 | 0 | 30000 | 1800 | 31800
|  |  | 1.3 | Regionally developed WTBD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1.4 | Press conferences |  | 0 | 10000 | 40000 | 0 | 0 | 3000 | 53000
|  |  | 1.5 | Video news release |  | 0 | 0 | 20000 | 0 | 0 | 1200 | 21200
|  |  | 1.6 | Enter PE Title |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | Training & networking |  |  | ML | 0 | 50000 | 0 | 100000 | 0 | 9000 | 159000
|  |  | 2.1 | Media trainings |  | 0 | 20000 | 0 | 100000 | 0 | 7200 | 127200
|  |  | 2.2 | Networking to expand number of TB advocacy partners |  | 0 | 30000 | 0 | 0 | 0 | 1800 | 31800
| 3 | ACTION project |  |  | ML | 0 | 30000 | 0 | 0 | 0 | 1800 | 31800
|  |  | 3.1 | Advocacy strategy for donor countries |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 3.2 | Media activities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 3.3 | Coordinator travel |  | 0 | 30000 | 0 | 0 | 0 | 1800 | 31800
| 4 | Media relations |  |  | ML | 0 | 30000 | 90000 | 0 | 0 | 7200 | 127200
|  |  | 4.1 | Press conferences & Donor country media tours |  | 0 | 30000 | 90000 | 0 | 0 | 7200 | 127200
| 5 | Web site |  |  | SR | 0 | 0 | 0 | 0 | 20000 | 1200 | 21200
|  |  | 5.1 | Editorial management, production of new content & on line fundraising |  | 0 | 0 | 0 | 0 | 20000 | 1200 | 21200
| 6 | Internal communication (with in TB community) |  |  | ML | 0 | 0 | 15000 | 0 | 0 | 900 | 15900
|  |  | 6.1 | Communiqués & e-forums |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Surveys |  | 0 | 0 | 15000 | 0 | 0 | 900 | 15900
| 7 | Product development |  |  | ML | 0 | 0 | 150000 | 0 | 0 | 9000 | 159000
|  |  | 7.1 | Writing , editing , design & layout of published materials, reports , info packs, CD/DVD |  | 0 | 0 | 150000 | 0 | 0 | 9000 | 159000
| 8 | Information products |  |  | ML | 0 | 0 | 0 | 0 | 70000 | 4200 | 74200
|  |  | 8.1 | Printing and distribution |  | 0 | 0 | 0 | 0 | 70000 | 4200 | 74200
| 9 | Audio/Video products |  |  | ML | 0 | 0 | 110000 | 0 | 0 | 6600 | 116600
|  |  | 9.1 | Audio visual product & educative films |  | 0 | 0 | 110000 | 0 | 0 | 6600 | 116600
| 10 | Advocacy Communication & Social Mobilization working group support |  |  | ML | 0 | 10000 | 0 | 140000 | 0 | 9000 | 159000
|  |  | 10.1 | Meetings and formulation of working group work plan |  | 0 | 10000 | 0 | 140000 | 0 | 9000 | 159000
|  |  | 10.2 | Web site maintenance, conference calls, reports and information dissemination |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11 | Coordination with other working groups |  |  | ML | 0 | 15000 | 0 | 0 | 0 | 900 | 15900
|  |  | 11.1 | Global plan two launch coordination & web site maintenance |  | 0 | 15000 | 0 | 0 | 0 | 900 | 15900
| 12 | General management |  |  | ML | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 12.1 | Retreats, PMDS, meetings, personal & human resource management |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13 | Global Advocacy Staff |  |  | ML | 910000 | 0 | 0 | 0 | 0 | 54600 | 964600
|  |  | 13.1 | Luhan Michael |  | 421000 | 0 | 0 | 0 | 0 | 25260 | 446260
|  |  | 13.2 | Rozario Shalu |  | 267000 | 0 | 0 | 0 | 0 | 16020 | 283020
|  |  | 13.3 | Burnier Isabelle |  | 222000 | 0 | 0 | 0 | 0 | 13320 | 235320

## ACSM part2
Stop TB Partnership Work plan (Schedule 3)
Component |  | Product/Service |  | Activity | Resp. Officer | Salaries | Travel | Contractual Services | Meeting | Publication Distribution | Direct Fin support/ country | PSC | Total
C3. Advocacy Communication and Social Moblization (ACSM)
SC2. Country Level Advocacy and Communication and SM
|  |  |  | Total Sub-component Cost |  | 559000 | 175000 | 635000 | 277000 | 20000 | 0 | 99960 | 1765960
| 1 | Capacity building in regions - ACSM at County Level |  |  | PT | 0 | 95000 | 535000 | 240000 | 0 | 0 | 52200 | 922200
|  |  | 1.1 | Syllable development |  | 0 | 40000 | 90000 | 0 | 0 | 0 | 7800 | 137800
|  |  |  | Trainings |  | 0 | 40000 | 260000 | 0 | 0 | 0 | 18000 | 318000
|  |  | 1.2 | Guidelines development |  | 0 | 0 | 150000 | 0 | 0 | 0 | 9000 | 159000
|  |  | 1.3 | Adoption, translation of ACSM tools for country level |  | 0 | 0 | 30000 | 0 | 0 | 0 | 1800 | 31800
|  |  | 1.4 | Three GFATM training workshops |  | 0 | 15000 | 0 | 240000 | 0 | 0 | 15300 | 270300
|  |  | 1.5 | Technical Assistance and consultations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1.6 | Strategic communication focal point at regional level |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1.7 | Project management and planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1.8 | Facilitate the formation of ACS partnerships and task forces |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1.9 | Research and development of four new ACS products and tools |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1.1 | Creation of a database for collecting , analyzing and reporting on country level ACS intervention |  | 0 | 0 | 5000 | 0 | 0 | 0 | 300 | 5300
| 2 | Sub-Group on ACS at Country Level |  |  | PT | 0 | 80000 | 100000 | 27000 | 20000 | 0 | 13620 | 240620
|  |  | 2.1 | Secretariat functions, meetings, conference calls and administrative coordination |  | 0 | 30000 | 0 | 27000 | 0 | 0 | 3420 | 60420
|  |  | 2.2 | Web site maintenance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2.3 | Monitoring evaluation and research of SG work plan |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2.4 | Desktop publishing and information dissemination |  | 0 | 0 | 0 | 0 | 20000 | 0 | 1200 | 21200
|  |  | 2.5 | Planning, implementation and conclusion of ACS country level activities |  | 0 | 50000 | 100000 | 0 | 0 | 0 | 9000 | 159000
|  |  | 2.6 | Report writing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2.7 | Technical assistance brokering |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Project management |  |  | PT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 3.1 | Planning , implementation and conclusion partnership secretariat ACS team activities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Coordination with other Working Groups |  |  | PT | 0 | 0 | 0 | 10000 | 0 | 0 | 600 | 10600
|  |  | 4.1 | Meetings |  | 0 | 0 | 0 | 10000 | 0 | 0 | 600 | 10600
|  |  | 4.2 | Web site maintenance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | County Level Advocacy team staff |  |  | PT | 559000 | 0 | 0 | 0 | 0 | 0 | 33540 | 592540
|  |  | 5.1 | Pennas Thaddeus |  | 366000 | 0 | 0 | 0 | 0 | 0 | 21960 | 387960
|  |  | 5.2 | Twal Hanan |  | 193000 | 0 | 0 | 0 | 0 | 0 | 11580 | 204580

## ACSM part3
Stop TB Partnership Work plan (Schedule 3)
Component |  | Product/Service | Activity | Resp Officer | Salaries | Travel | Contractual | Meeting | Publication | PSC | Total
C3. Advocacy, Communication and Social Mobilisation (ACSM)
SC3.TB-affected community empowerment and mobilization
|  |  | Total Sub-component Cost |  | 179556 | 50000 | 200000 | 110000 | 15000 | 33273.36 | 587829.36
| 1 | Capacity building at regional level |  | TT | 0 | 20000 | 0 | 80000 | 0 | 6000 | 106000
|  | 1.1 | Four training workshops, each in in |  | 0 | 20000 | 0 | 80000 | 0 | 6000 | 106000
| 2 | Manual /guidelines for NTP on patient empowerment and involvement |  | TT | 0 | 20000 | 95000 | 0 | 0 | 6900 | 121900
|  | 2.1 | Documentation and analysis of patients experiences |  | 0 | 10000 | 20000 | 0 | 0 | 1800 | 31800
|  | 2.2 | Draft guidelines |  | 0 | 0 | 10000 | 0 | 0 | 600 | 10600
|  | 2.3 | Field testing of draft guidelines |  | 0 | 5000 | 15000 | 0 | 0 | 1200 | 21200
|  | 2.4 | Implementation |  | 0 | 5000 | 20000 | 0 | 0 | 1500 | 26500
|  | 2.5 | Evaluation |  | 0 | 0 | 30000 | 0 | 0 | 1800 | 31800
| 3 | Network development |  | TT | 0 | 0 | 30000 | 30000 | 0 | 3600 | 63600
|  | 3.1 | Participation in meetings, conferences, web development and newsletters |  | 0 | 0 | 30000 | 30000 | 0 | 3600 | 63600
| 4 | Patient Charter |  | TT | 0 | 10000 | 35000 | 0 | 15000 | 3600 | 63600
|  | 4.1 | Participate in development of the charter |  | 0 | 5000 | 5000 | 0 | 0 | 600 | 10600
|  | 4.2 | Distribution and monitoring of the charter |  | 0 | 0 | 0 | 0 | 15000 | 900 | 15900
|  | 4.3 | Evaluation of the impact of the charter |  | 0 | 5000 | 30000 | 0 | 0 | 2100 | 37100
| 5 | Regional TB courses |  | TT | 0 | 0 | 20000 | 0 | 0 | 1200 | 21200
|  | 5.1 | Develop half day training component on patient empowerment and involvement |  | 0 | 0 | 5000 | 0 | 0 | 300 | 5300
|  | 5.2 | Conducting four courses |  | 0 | 0 | 15000 | 0 | 0 | 900 | 15900
| 6 | Patient focal person in the stop TB secretariat |  | TT | 0 | 0 | 20000 | 0 | 0 | 1200 | 21200
|  | 6.1 | Coordinate activities projects and maintain visible the TB affected community with in WHO and TBP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6.2 | Document stories on TB patients experiences |  | 0 | 0 | 20000 | 0 | 0 | 1200 | 21200
| 7 | TB affected community empowerment staff |  | TT | 179556 | 0 | 0 | 0 | 0 | 10773.36 | 190329.36
|  | 7.1 | Torfoss Ted |  | 179556 | 0 | 0 | 0 | 0 | 10773.36 | 190329.36

## RES MOB.
Stop TB Partnership Work plan (Schedule 3)
Component |  | Product/Service |  | Activity | Resp. Officer | Salaries | Travel | Contractual Services | Gen. Expenses | Meeting | Publication Distribution | PSC | Total
C4. Resource Mobilization |  |  |  | Total Component Cost |  | 267000 | 75000 | 195500 | 31000 | 0 | 90000 | 39510 | 698010
| 1 | Grant agreements reached with new donors |  |  | MH | 0 | 20000 | 0 | 2000 | 0 | 0 | 1320 | 23320
|  |  | 1.1 | Conduct desk research |  | 0 | 0 | 0 | 2000 | 0 | 0 | 120 | 2120
|  |  | 1.2 | Launch series of segment marketing campaigns |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1.3 | Gather donor intelligence |  | 0 | 10000 | 0 | 0 | 0 | 0 | 600 | 10600
|  |  | 1.4 | Prepare grant proposals |  | 0 | 10000 | 0 | 0 | 0 | 0 | 600 | 10600
| 2 | Grant agreement with private companies |  |  | MH | 0 | 10000 | 73000 | 1000 | 0 | 0 | 5040 | 89040
|  |  | 2.1 | Conduct desk research |  | 0 | 0 | 1500 | 0 | 0 | 0 | 90 | 1590
|  |  | 2.2 | Identify a target group of private corporations and establish contact |  | 0 | 0 | 1500 | 1000 | 0 | 0 | 150 | 2650
|  |  | 2.3 | Prepare and launch a series of segments marketing campaigns |  | 0 | 0 | 70000 | 0 | 0 | 0 | 4200 | 74200
|  |  | 2.4 | Gather company intelligence |  | 0 | 10000 | 0 | 0 | 0 | 0 | 600 | 10600
|  |  | 2.5 | Hold informational meetings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2.6 | Prepare project proposals |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Individual donor and supporter programmed |  |  | MH | 0 | 0 | 30000 | 1000 | 0 | 0 | 1860 | 32860
|  |  | 3.1 | Conduct research to identify target individuals, constituencies and specific subsegements |  | 0 | 0 | 10000 | 1000 | 0 | 0 | 660 | 11660
|  |  | 3.2 | Prepare an outreach plan to each segments |  | 0 | 0 | 10000 | 0 | 0 | 0 | 600 | 10600
|  |  | 3.3 | Design and develop individual donors & supporters plan |  | 0 | 0 | 10000 | 0 | 0 | 0 | 600 | 10600
| 4 | Online marketing program |  |  | MH | 0 | 0 | 54000 | 1000 | 0 | 0 | 3300 | 58300
|  |  | 4.1 | Conduct market analysis |  | 0 | 0 | 10000 | 1000 | 0 | 0 | 660 | 11660
|  |  | 4.2 | Design and develop an online marketing programmed |  | 0 | 0 | 10000 | 0 | 0 | 0 | 600 | 10600
|  |  | 4.3 | Formulate an implementation plan |  | 0 | 0 | 10000 | 0 | 0 | 0 | 600 | 10600
|  |  | 4.4 | Operate the programmed |  | 0 | 0 | 24000 | 0 | 0 | 0 | 1440 | 25440
| 5 | Events information booths |  |  | MH | 0 | 30000 | 20000 | 6000 | 0 | 0 | 3360 | 59360
|  |  | 5.1 | Identify conferences and events related to key stop TB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 5.2 | Position stop TB staff to make presentation at the events |  | 0 | 30000 | 20000 | 6000 | 0 | 0 | 3360 | 59360
| 6 | Annual fund raising gala |  |  | MH | 0 | 15000 | 10000 | 5000 | 0 | 0 | 1800 | 31800
|  |  | 6.1 | Form a planning committee |  | 0 | 0 | 0 | 1000 | 0 | 0 | 60 | 1060
|  |  | 6.2 | Identify partner institutions to work with on fund raising galas |  | 0 | 15000 | 0 | 0 | 0 | 0 | 900 | 15900
|  |  | 6.3 | Prepare a business plan |  | 0 | 0 | 0 | 1000 | 0 | 0 | 60 | 1060
|  |  | 6.4 | Communicate the events with partners, donors and supporters |  | 0 | 0 | 10000 | 3000 | 0 | 0 | 780 | 13780
| 7 | Donor profile |  |  | MH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 7.1 | Conduct research and analysis of donor information and compile profile report |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | Policy research on emerging issues |  |  | MH | 0 | 0 | 0 | 5000 | 0 | 30000 | 2100 | 37100
|  |  | 8.1 | Develop a term of reference for consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 8.2 | Prepare and disseminate the report |  | 0 | 0 | 0 | 5000 | 0 | 30000 | 2100 | 37100
| 9 | New service/product line investment strategy and proposal for new service/product line |  |  | MH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 9.1 | Conduct research and analysis of new product and services |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | Issue focused donors brochures (two) |  |  | MH | 0 | 0 | 6000 | 3000 | 0 | 28000 | 2220 | 39220
|  |  | 10.1 | Draft, design , print and distribute brochures |  | 0 | 0 | 6000 | 3000 | 0 | 28000 | 2220 | 39220
| 11 | Stop TB Partnership calendars for 2007 |  |  | MH | 0 | 0 | 2500 | 3000 | 0 | 0 | 330 | 5830
|  |  | 11.1 | Design, print, prepare distribution list and distribute calendars |  | 0 | 0 | 2500 | 3000 | 0 | 0 | 330 | 5830
| 12 | Biannual business plan |  |  | MH | 0 | 0 | 0 | 3000 | 0 | 28000 | 1860 | 32860
|  |  | 12.1 | Design, print and disseminate the plan |  | 0 | 0 | 0 | 3000 | 0 | 28000 | 1860 | 32860
| 13 | Donor business gift and accessories |  |  | MH | 0 | 0 | 0 | 1000 | 0 | 4000 | 300 | 5300
|  |  | 13.1 | Prepare an item development plan, design and produce and distribute items |  | 0 | 0 | 0 | 1000 | 0 | 4000 | 300 | 5300
| 14 | Resource mobilization staff |  |  | MH | 267000 | 0 | 0 | 0 | 0 | 0 | 16020 | 283020
|  |  | 14.1 | Hayakawa Motoky |  | 267000 | 0 | 0 | 0 | 0 | 0 | 16020 | 283020

## Admin&Infrast'l Support
Stop TB Partnership Work plan (Schedule 3)
Component |  | Product/Service |  | Activity | Resp. Officer | Salaries | Travel | Contractual Services | Transl. Publishing and Distribution | Supplies and materials | PSC | Total
C5. Administration and Infrastructural Support |  |  |  | Total Component Cost |  | 1701000 | 30000 | 1148354 | 38000 | 62000 | 178761.24 | 3158115.24
SC1. Existing Donor Relations |  |  |  | Total Sub-component Cost |  | 0 | 30000 | 105000 | 15000 | 0 | 9000 | 159000
| 1 | Grant agreements with new donors |  |  | AV | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1.1 | Draft grant agreements with new donors |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1.2 | Negotiate and finalise donor agreement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | Enhanced donor relationships |  |  | AV | 0 | 30000 | 0 | 0 | 0 | 1800 | 31800
|  |  | 2.1 | Follow up of donor agreements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2.2 | Update donor profiles |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2.3 | Hold donor meetings |  | 0 | 30000 | 0 | 0 | 0 | 1800 | 31800
| 3 | Donor survey |  |  | AV | 0 | 0 | 60000 | 0 | 0 | 3600 | 63600
|  |  | 3.1 | Update survey |  | 0 | 0 | 30000 | 0 | 0 | 1800 | 31800
|  |  | 3.2 | Meetings on donor resource tacking |  | 0 | 0 | 25000 | 0 | 0 | 1500 | 26500
|  |  | 3.3 | Obtain revenue data |  | 0 | 0 | 5000 | 0 | 0 | 300 | 5300
|  |  | 3.4 | Map WHO data set to TBP data set | [6 empty] | 0 | 0
| 4 | Financial flow from budgetary support & SWAP for TB control |  |  | AV | 0 | 0 | 45000 | 15000 | 0 | 3600 | 63600
|  |  | 4.1 | Undertake study |  | 0 | 0 | 45000 | 0 | 0 | 2700 | 47700
|  |  | 4.2 | Disseminate reports |  | 0 | 0 | 0 | 15000 | 0 | 900 | 15900
| 5 | Donor financial report |  |  | AV | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 5.1 | Prepare Financial Reports |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | Technical reports |  |  | AV | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 6.1 | Obtaining progress report from receipients of funds |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 6.2 | Compile reports for donors |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
SC2. Financial Management |  |  |  | Total Sub-component Cost |  | 0 | 0 | 135000 | 15000 | 0 | 9000 | 159000
| 1 | Quarterly appropriation report |  |  | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1.1 | Complie appropriation requests |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1.2 | Review allotment utilisation, available fund and make recommendation for allotment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | Monthly Financial Statements |  |  | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2.1 | Prepare monthly cash statements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2.2 | Prepare allotment balances for TBP units | [6 empty] | 0 | 0
| 3 | Financial Forecasts |  |  | AV | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 3.1 | Developing a Model |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 3.2 | Obtaining data from the Financial System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Partnership and GDF financial reports |  |  | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 4.1 | Obtain data from WHO system and UN web buy |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 4.2 | Analyse data and prepare financial reports |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 4.3 | Check financial reports |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | Procurement Agreements |  |  | AV | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 5.1 | Draft procurement agent agreements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 5.2 | Review financial and legal aspect of agent agreements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 5.3 | Coordinate amendement and extension of agreements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | Payment to procurement agent(s) PA |  |  | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 6.1 | Check PA invoices, and match with firm purchase orders, check supporting documents and prepare payment request |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 6.2 | Monitor implementation of contractual terms |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 6.3 | Review invoices and payment requests and clear payments |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | Manage Operational Flow of work |  |  | AV | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 7.1 | Check APW for financial and procedural accuracy |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 7.2 | Check adjudication reports |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 7.3 | Clear APW payments |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | Operate Internal Financial Control |  |  | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 8.1 | Implement control in Revenue, Payment, Procurement cycles |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | Financial management system for TBP |  |  | AV | 0 | 0 | 50000 | 0 | 0 | 3000 | 53000
|  |  | 9.1 | Prepare the architecture of a financial management system using data from AFI and other centralised system of WHO |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 9.2 | Select a platform and implement the architecture |  | 0 | 0 | 50000 | 0 | 0 | 3000 | 53000
|  |  | 9.3 | Supervision and Review of all Financial Operations | [6 empty] | 0 | 0
| 10 | Computerised finacial management system |  |  | AV | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 10.1 | Design the system as per agreed Arcitecture | [6 empty] | 0 | 0
|  |  | 10.2 | Test computerised FM system |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 10.3 | Operate the system to generate reports required |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11 | Tools for performace assessement |  |  | AV | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 11.1 | Design financial analytics for performance measurement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12 | PRSP toolkit for mainstreaming TB control into PRSPs |  |  | AV | 0 | 0 | 85000 | 15000 | 0 | 6000 | 106000
|  |  | 12.1 | Design and dvelop the toolkit |  | 0 | 0 | 70000 | 0 | 0 | 4200 | 74200
|  |  | 12.2 | Hold consultative workshops with stakeholders |  | 0 | 0 | 15000 | 0 | 0 | 900 | 15900
|  |  | 12.3 | Finalise and print Toolkit including CD ROM version |  | 0 | 0 | 0 | 15000 | 0 | 900 | 15900
| 13 | Workplan 2008 - 2009 |  |  | AV | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 13.1 | Compile and input data |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
SC3. Personnel and General administration |  |  |  | Total Sub-component Cost |  | 1335000 | 0 | 807000 | 8000 | 0 | 129000 | 2279000
| 1 | Manage grant to receipients |  |  | AV | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1.1 | Prepare grant agreements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1.2 | Monitor grant agreements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | Progress reports 2005 & 2006 |  |  | AV | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2.1 | Draft report text |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2.2 | Design and print reports |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2.3 | Disseminate the reports |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Five year achievement report |  |  | AV | 0 | 0 | 7000 | 8000 | 0 | 900 | 15900
|  |  | 3.1 | Design and editing |  | 0 | 0 | 7000 | 0 | 0 | 420 | 7420
|  |  | 3.2 | Print and disseminate |  | 0 | 0 | 0 | 8000 | 0 | 480 | 8480
| 4 | External evaluation of partnership and GDF |  |  | AV | 0 | 0 | 800000 | 0 | 0 | 48000 | 848000
|  |  | 4.1 | Issue RFP and select consultants |  | 0 | 0 | 800000 | 0 | 0 | 48000 | 848000
|  |  | 4.2 | Arrange for a schedule of work for the consultants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 4.3 | Receive and discuss final draft |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 4.4 | Excom meeting for discussing the report |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 4.5 | Finalisation and dissemination of the report |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 4.6 | Preparing response to the evaluation report |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 4.7 | Preparing next step for implementing accepted recommendations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | Manage Human Resource Services |  |  | AV | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 5.1 | Prepare documents for contract management extension, financing etc |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 5.2 | Prepare financial requirement schedule for staff |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 5.3 | Review HR management of work |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | MOU with WHO |  |  | AV | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 6.1 | Drafting MOU |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 6.2 | Supporting the CB members for negotiation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | Financial and Operations Management Staff |  |  | AV | 1335000 | 0 | 0 | 0 | 0 | 80100 | 1415100
|  |  | 7.1 | Anant Vijay |  | 421000 | 0 | 0 | 0 | 0 | 25260 | 446260
|  |  | 7.2 | Ababor Nejib |  | 306000 | 0 | 0 | 0 | 0 | 18360 | 324360
|  |  | 7.3 | Weerasinghe Roy, Sulo |  | 222000 | 0 | 0 | 0 | 0 | 13320 | 235320
|  |  | 7.4 | Baclig Luz |  | 193000 | 0 | 0 | 0 | 0 | 11580 | 204580
|  |  | 7.5 | Johnson Eben |  | 193000 | 0 | 0 | 0 | 0 | 11580 | 204580
SC4. Information Technology |  |  |  | Total Sub-component Cost |  | 366000 | 0 | 101354 | 0 | 62000 | 31761.24 | 561115.24
| 1 | Stop TB partnership web site |  |  | RM | 0 | 0 | 4000 | 0 | 0 | 240 | 4240
|  |  | 1.1 | Update the content of the TBP web site and its sub sites |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1.2 | Implement a content management system for web site |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1.3 | APW for content management system implementation |  | 0 | 0 | 4000 | 0 | 0 | 240 | 4240
|  |  | 1.4 | Web site architecture , design, management and monitoring |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1.5 | keep the weekly news items and events calander updated |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | World TB day 2006 & 2007 |  |  | RM | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2.1 | Design and build the world TB day 2006 & 2007 sites |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Stop TB partnership mail list and email box |  |  | RM | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 3.1 | Manage and maintain the mailing list |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 3.2 | Read incoming emails and reply or forward it as needed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Advocacy mailing |  |  | RM | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 4.1 | Build and send announcements, newsletters and communiqués |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | Business server |  |  | RM | 0 | 0 | 0 | 0 | 12000 | 720 | 12720
|  |  | 5.1 | Check the server logs, security and insure proper functionality |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 5.2 | New server |  | 0 | 0 | 0 | 0 | 12000 | 720 | 12720
| 6 | Application maintenace and development |  |  | RM | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 6.1 | Maintain update the existing secretariat applications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 6.2 | Design and develop new IT solutions where appropriate to meet emerging sevretariat business needs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | Global plan II |  |  | RM | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 7.1 | Develop the Global PIan II site using the vendor supplied templates |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | Web based resources mobiliszation |  |  | RM | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 8.1 | Work with the resource mobilisation officer to implement an online donation system |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | Third partner's forum web site |  |  | RM | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 9.1 | Design and build the Third Partner's Forum web site |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | IT strategic & IT work plan |  |  | RM | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 10.1 | Prepare and maintain the IT strategic plan |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 10.2 | Prepare and maintain the IT work plan |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11 | User support |  |  | RM | 0 | 0 | 96000 | 0 | 0 | 5760 | 101760
|  |  | 11.1 | Assist users with their IT issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 11.2 | Liaise with WHO IT staff as needed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 11.3 | Receive services from central IT department |  | 0 | 0 | 96000 | 0 | 0 | 5760 | 101760
| 12 | Repositoire of guidelines, best practices and standard operating procedures |  |  | RM | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 12.1 | Compile guidelines, best practicies and SOPs in on line place |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 12.2 | Help TBP staff adhere to guidelines, SOPs and best practicies |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13 | Hardware inventory |  |  | RM | 0 | 0 | 0 | 0 | 50000 | 3000 | 53000
|  |  | 13.1 | Manage the harware inventory |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 13.2 | New hardware and software procurement |  | 0 | 0 | 0 | 0 | 50000 | 3000 | 53000
| 14 | Administrative support and CD/DVD duplication |  |  | RM | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 14.1 | Run duplication job as specified in the plan |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 14.2 | Handle administrative task and process administrative formes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 | Secretariat work planning system based on the TBP work plan |  |  | RM | 0 | 0 | 1354 | 0 | 0 | 81.24 | 1435.24
|  |  | 15.1 | Design and build a shared point system for work planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 15.2 | Set up the intergration with AMS |  | 0 | 0 | 1354 | 0 | 0 | 81.24 | 1435.24
| 16 | Financial reporting interface |  |  | RM | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 16.1 | Advise on the selection of the package |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 17 | New shared drive structure |  |  | RM | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 17.1 | Restructure the first level folder |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 18 | Partners' Directory |  |  | RM | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 18.1 | Maintain, design and develop the Partners' Directory as needed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 19 | National Partnership IT Package |  |  | RM | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 19.1 | Develop an IT package containing identified components to aid and enhance the IT capacity of the exisiting national partnerships |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 19.2 | Establish a mechanisim for delivering the IT package to the national partnerships |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 19.3 | Consolidate the contents of all the national level partners directories at the global level |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 20 | Information Technology staff |  |  | RM | 366000 | 0 | 0 | 0 | 0 | 21960 | 387960
|  |  | 20.1 | Maggi Richard |  | 366000 | 0 | 0 | 0 | 0 | 21960 | 387960

## GDF
Stop TB Partnership Work plan (Schedule 3)
Component |  | Product/Service | Activity | Resp. Officer | Salaries | Travel | Contractual Services | Gen. Expenses | Meeting | Publication Distribution | Direct Fin Support/country | Supplies | PSC | Total
C6. GDF |  |  | Total Component Cost |  | 2999000 | 92000 | 3291200 | 0 | 694100 | 102000 | 0 | 61900000 | 2287698 | 71365998
SC1. Application, Review and Monitoring |  |  | Total Sub-component Cost |  | 1300000 | 0 | 827200 | 0 | 563000 | 0 | 0 | 0 | 161412 | 2851612
| 1 | Application and review process for GDF |  | AT | 0 | 0 | 74200 | 0 | 315000 | 0 | 0 | 0 | 23352 | 412552
|  | 1.1 | Announcement for applications for GDF grants for 1st line TB drugs and DP and diagnostics |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.2 | Regular update of all applications to include baseline indicators to ensure harmonization with CV guidelines and monitoring checklist |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.3 | Coordinate GDF applications with GFATM |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.4 | Screening and review of applications for first line drugs and diagnostics by the technical review committee (TRC) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.5 | Coordination of TRC meetinsg |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.6 | TRC meeting |  | 0 | 0 | 0 | 0 | 315000 | 0 | 0 | 0 | 18900 | 333900
|  | 1.7 | TRC logistics |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.8 | Update TOR for TRC to include diagnostics and pediatrics |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.9 | TRC minutes produced and distributed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.91 | Follow up on recommendation made from the TRC to the country, partners and GDF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.92 | Development of mechanisim for DP review |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.93 | Pre delivery missions for GDF applications |  | 0 | 0 | 74200 | 0 | 0 | 0 | 0 | 0 | 4452 | 78652
|  | 1.94 | Mission information including SOW and documents updated for consultant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.95 | Distribution of recommendation from pre delivery missions to all stakholders |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.96 | Grant agreement for GDF (1st, 2nd and 3rd year) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.97 | Technical agreements for direct procurement (DP) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.98 | Develop application mechanism for TB diagnostics |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.99 | Update and monitor the KMS with all country information on application and review |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.991 | Coordination of GDF application and review activities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | GDF monitoring, GDF monitoring review and review of processes and documents |  | AT | 0 | 0 | 658000 | 0 | 0 | 0 | 0 | 0 | 39480 | 697480
|  | 2.1 | Streamline mechanisims to follow up on recommendations from TRC, desk audit and monitoring missions to NTP, partners and GDF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.2 | Develop diagnostic indicators and mechanism for diagnostics |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.3 | Develop monitoring mechanism |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.4 | Develop monitoring mechanism for pediatrics |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.5 | Review and update first line TB drug inidcator to assess GDF impact on countries |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.6 | Update standard monitoring checklist tool for assessement of first line TB drugs for grant and DP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.7 | Collect annual and quarterly reports |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.8 | Monitoring mission to GDF supported countries |  | 0 | 0 | 541800 | 0 | 0 | 0 | 0 | 0 | 32508 | 574308
|  | 2.9 | Keep all mission information including SOW and documents updated for consultants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.91 | Distribute recommendations from monitoring missions to appropriate stakeholders |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.92 | Assessement of monitoring dossier by GDF desk audit agency |  | 0 | 0 | 116200 | 0 | 0 | 0 | 0 | 0 | 6972 | 123172
|  | 2.93 | Update and monitor KMS with all coutry information for monitoring |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.94 | Ongoing development of monitoring processes and documents |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.95 | Participation in TB coordination meeting |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.96 | Establishing and collaborating with regional focal points |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.97 | Coordination of GDF monitoring activities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Improve drug management in GDF supported countries |  | AT | 0 | 0 | 0 | 0 | 248000 | 0 | 0 | 0 | 14880 | 262880
|  | 3.1 | Involvement in regional drug management (DM) meetings |  | 0 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 2880 | 50880
|  | 3.2 | Develop an external partner coordination mechanisim for DM issues identified through GDF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.3 | Provideing DM recommendations to countries from TRC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.4 | Providing recommendations to countries from monitoring mission |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.5 | Pre delivery mission to include collection of standardized data on DM |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.6 | Training of consultants in every region |  | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 12000 | 212000
| 4 | Technical Assistance (TA) service line in drug management |  | AT | 0 | 0 | 95000 | 0 | 0 | 0 | 0 | 0 | 5700 | 100700
|  | 4.1 | Developement of the TA service line strategy in collaborataion with TRC |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1200 | 21200
|  | 4.2 | GDF proposed TA service line to coordinating board |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.3 | Public announcement of new TA services |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.4 | Developement of of advocacy and communication materials for new TA services |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.5 | TA service line implemented |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 4500 | 79500
|  | 4.6 | Evaluation of TA service line |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | Strategy development in collaboration with DEWG and PSM to promote use of FDCs |  | AT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.1 | Regular meeting with DEWG, PSM, GFATM, MSH, JSI to update and collaborate with DM issues |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | Partner mobilization |  | AT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6.1 | Map and update on regular basis STB partners and their activities in all countries receiving GDF drugs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6.2 | Prepare template letter outlining the role of GDF and expectations of partner provided TA to be sent to principal partners following grant approval |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6.3 | GDF staff member to serve as focal point on the recently formed ad-hoc working group on technical support (TBS) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | GDF Application review and monitoting staff |  | AT | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78000 | 1378000
|  | 7.1 | Castel Helen |  | 267000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16020 | 283020
|  | 7.2 | Hernandez Homero Luis |  | 267000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16020 | 283020
|  | 7.3 | Kogevinas Desiree |  | 267000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16020 | 283020
|  | 7.4 | Perrin Jeanne-Françoise |  | 193000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11580 | 204580
|  | 7.5 | Thomas Adam |  | 306000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18360 | 324360
SC2. Procurement and Supply |  |  | Total Sub-component Cost |  | 499000 | 12000 | 986000 | 0 | 68100 | 0 | 0 | 61900000 | 1950906 | 65416006
| 1 | Improved quality of 1st and 2nd line TB drugs |  | RM | 0 | 0 | 820000 | 0 | 0 | 0 | 0 | 0 | 49200 | 869200
|  | 1.1 | Commission, maintain and safeguard on-going pre qualification project |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.2 | Issue expression of interest (EOI) for participation in pre-qualification process and posting on web and IDBR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.3 | Receipt of EOIs and issuance of guidelines for dossier submission by PSM/QSM |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.4 | Review of product dossiers from suppliers by PSM/QSM |  | 0 | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 13200 | 233200
|  | 1.5 | GMP physical site inspection of manufacturers by PSM/QSM |  | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 18000 | 318000
|  | 1.6 | Coordination with QSM, regular update monthly meeting |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.7 | Training workshop with manufacturers & NRA officials |  | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 12000 | 212000
|  | 1.8 | Creation of roster of consultants providing TA to suppliers participating in pre-qualification project |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 6000 | 106000
| 2 | Selection of new GDF suppliers 1st and 2nd line TB drugs |  | RM | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | 12720
|  | 2.1 | Provide input to procurument agent (PA) for finalization of ITB letter (forecast, list of eligible products per supplier, guidelines on stockpile management, branding, packaging templates) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.2 | Provide input on final LTAs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.3 | Assist PA with adjudication of bids (technical) |  | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | 12720
0
| 3 | Selection of new GDF 1st line procurument agent |  | RM | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 360 | 6360
|  | 3.1 | Issue EOI to procurument agents (publish in website, IDBR, scrip/ Economist) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.2 | Prepare , issue RFP, adjusdicaion of proposals for PAs and contracting of new PA |  | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 360 | 6360
| 4 | Efficient supply of quality 1st and 2nd line anti TB drugs |  | RM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61900000 | 1857000 | 63757000
|  | 4.1 | Placing order with PA for grant and DP (1st line) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.2 | Monitor order request and placement by project to PA (2nd line) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.3 | Cost of drug 1st line |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000000 | 1350000 | 46350000
|  | 4.4 | Cost of drug 2nd line |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 3000 | 103000
|  | 4.5 | Quality control and pre-shipment inspection comment on QC agent remarks (1st line) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700000 | 81000 | 2781000
|  | 4.6 | QC and pre-shipment comment on QC agent remarks (2nd line) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 18000 | 618000
|  | 4.7 | Shipping, freight and insurance (1st line) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500000 | 405000 | 13905000
|  | 4.8 | Shipping, freight and insurance (2nd line) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.9 | Information management (hard copy and electronic filing ). Sharepoint organization and updating in PRS secion |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | Improved delivery lead times and monitoring of supply through close coordination of supply agents for 1st and 2nd line drugs and effective management of anti-TB drugs stockpile(s) |  | RM | 0 | 0 | 25000 | 0 | 68100 | 0 | 0 | 0 | 5586 | 98686
|  | 5.1 | Regular communication and video conferences (booking of conference facilities) |  | 0 | 0 | 0 | 0 | 8100 | 0 | 0 | 0 | 486 | 8586
|  | 5.2 | Super team meetings with contractual partners for supply |  | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 3600 | 63600
|  | 5.3 | Management tool to monitor agent performance and lead time |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 1500 | 26500
|  | 5.4 | Monitor implementation of SOPs to ensure efficient payment of PA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.5 | Develop and take action on reports generated from system |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | Accurate forcasting of 1st and 2nd line anti TB drug needs |  | RM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6.1 | Forecasting: Develop accurate quarterly forecasts in conjunction with ARM, GMS, & PA for suppliers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | Develop a procurement and distribution strategy for diagnostics equipment |  | RM | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 3600 | 63600
|  | 7.1 | Completion of pilot study for dagnostic kits |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 1800 | 31800
|  | 7.2 | Revise specifications of diagnostic kits based on outcomes of pilot studies and comparative assessement of microscope kits from different suppliers |  | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 1800 | 31800
| 8 | Efficient supply of diagnostics equipment |  | RM | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 2400 | 42400
|  | 8.1 | Finalize Pilot assessments |  |  |  | 30000 | [5 empty] | 1800
|  | 8.2 | Provide input to PA agent for ITB process , EOI, ITB, adjudication, contracting and issue of RFP |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 600 | 10600
|  | 8.3 | Placing order with PA for grant and DP |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8.4 | Cost of kits |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8.5 | Quality control and pre-shippment inspection and comment on QC agent remarks |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8.6 | Shipping, freight and insurance |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | Plan capacity building initiatives for clients with weak procurement and quality assurance system |  | RM | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 2100 | 37100
|  | 9.1 | Consult partners and donors in palnning process. Develop plan and identify clients for implementation in 2006 |  | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 2100 | 37100
| 10 | Update TB drug market survey report, 1st and 2nd line |  | RM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 10.1 | Produce, distribute and analyse questionaires |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11 | GDF procurement and supply staff |  | RM | 499000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29940 | 528940
|  | 11.1 | Adu Vitalis |  | 193000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11580 | 204580
|  | 11.2 | Procurement Officer (P3) |  | 306000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18360 | 324360
|  | 11.3 | Vrakking Hugo |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SC3. General Management and Support |  |  | Total Sub-component Cost |  | 1200000 | 80000 | 1478000 | 0 | 63000 | 102000 | 0 | 0 | 175380 | 3098380
| 1 | Demand assessment for GDF servicies (drugs , direct procurment and related products) |  | RM | 0 | 0 | 155000 | 0 | 0 | 0 | 0 | 0 | 9300 | 164300
|  | 1.1 | Assess demand for 1st and 2nd line TB drugs and related products and resource gap |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.2 | Contract demand assessement for 1st & 2nd line TB drugs and related products |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 900 | 15900
|  | 1.3 | Assess the demand for NGO applications for 1st & 2nd line drugs and related products |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.4 | Contract demand assessement for NGO applications for 1st & 2nd line TB drugs and related products |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 900 | 15900
|  | 1.5 | Assess demand for Direct Procurement (DP) by international agencies including GFATM, World Bank, regional banks and other major donors and develop marketing strategy for DP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.6 | Contract demand for DP |  | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 1500 | 26500
|  | 1.7 | Finalize marketing strategy |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.8 | Implementation of strategy |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 6000 | 106000
| 2 | Technical Assistance Service (TA) |  | RM | 306000 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 78360 | 1384360
|  | 2.1 | Develop strategy for formal TA service provision |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.2 | Secure funding for TA service including human resources |  | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 60000 | 1060000
|  | 2.3 | Maintain linkage with other TA service providers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.4 | Implement starategy |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.5 | Hire staff |  | 306000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18360 | 324360
|  | 2.6 | Ensure liaison with ARM |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Communication strategy for GDF |  | RM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.1 | Design strategy covering all aspects fo GDF external and internal PR and advocacy initiatives |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | GDF public relations |  | RM | 0 | 80000 | 20000 | 0 | 0 | 0 | 0 | 0 | 6000 | 106000
|  | 4.1 | Branding of GDF: marketing GDF brand as one of the most efficient, innovative and effective global health mechanisims available |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.2 | Presentation to key stakeholders (external PR) |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 42400
|  | 4.3 | Road show to key partners/donors |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1200 | 21200
|  | 4.4 | Client development/relations |  | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 42400
|  | 4.5 | Presentation to key stakeholders (internal PR) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.6 | Coordination with AMDS and MMSS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.7 | Coordination with internal (WHO-HQ & RO) technical partners: TBS/THD/TME, RAs, PSM/QSM |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.8 | Coordination with internal (WHO) executive and administrative officies:DGO, HR, FIN, country coordination, publication etc |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | Advocacy GDF |  | RM | 0 | 0 | 239000 | 0 | 0 | 67000 | 0 | 0 | 18360 | 324360
|  | 5.1 | Electronic promotional tools, enhance and develop new fact sheets, brochurs and other advocacy materials |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.2 | Review GDF fact sheets and other advocacy materials and identify gaps or changes required |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.3 | Update existing advocacy materials as required |  | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 2400 | 42400
|  | 5.4 | Contract developemnt of missing advocacy materials |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1200 | 21200
|  | 5.5 | Distribute update GDF advocacy materials including drug shipment |  | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 60 | 1060
|  | 5.6 | Publish GDF newletter - 2 issue and distribute to all partners |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.7 | Plan news letter development and delivery |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.8 | Distribute newsletter (paper and web) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.9 | Contract production of newletter text and design |  | 0 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 1440 | 25440
|  | 5.91 | Media video documentary system on GDF |  | 0 | 0 | 20000 | 0 | 0 | 2500 | 0 | 0 | 1350 | 23850
|  | 5.92 | Identify key messages and objectives of video documentary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.93 | Contract development, filming and post production work for documentary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.94 | work with partners and advocacy focal points to promote and target distribution of documentary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.95 | Improve GDF advocacy pack/define distribution |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.96 | Define objectives and contents of GDF advocacy kit as new GDF product |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.97 | Establish procedure for tracking and updating the advocacy materials in this kit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.98 | Establish procedure for distributing GDF advocacy kit and monitoring tock supplies in key offices |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.99 | Patient kit advocacy pack |  | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 360 | 6360
|  | 5.991 | Define contents/message of kit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.992 | Finalize content/message |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.993 | Crreat distribution list and distribut kit to target stakeholders |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.994 | NTP manager's kit |  | 0 | 0 | 25000 | 0 | 0 | 2500 | 0 | 0 | 1650 | 29150
|  | 5.995 | Develop strategic plan and objectives for NTP manager's kit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.996 | Coordinate with partners to identify and consolidate most effective tools and products for inclusion in manager's kit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.997 | Contract branding and marketing for manager's kit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.998 | Disseminate manager's kit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.999 | Enhancement, marketing and translation of GDF web site |  | 0 | 0 | 30000 | 0 | 0 | 5000 | 0 | 0 | 2100 | 37100
|  | 5.9991 | Define and actualize process for maintaining quality of information and product |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.9992 | Plan translation of web site and web site translation into French and Spanish |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.9993 | Actualize process for routinely translating new content for website |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.9994 | Ensure GDF coverage in global and medical media |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.9995 | Develop and document new angles on the GDF and messages suitable for public |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.9996 | Work with partners advocacy FPs to include GDF messages in suitable media |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.9997 | Journal coverage - write or outsource journal articles on GDF and its impact |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 900 | 15900
|  | 5.9998 | Identify appropirat themes and angles for GDF journal coverage |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.9999 | Contract writing of GDF journal articles |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.9999 | Submit articls for publication |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.9999 | Improve advocacy on rational for GDF standerdisation - promotion of existining document/position |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1200 | 21200
|  | 5.9999 | Promot brand GDF patient kits and blister packs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.9999 | Service promotion for grant |  | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 600 | 10600
|  | 6 | Service promotion for direct procurement |  | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 2100 | 37100
|  | 6 | Service promotion for prequalificaion services |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6 | Service promotion for technical assistance |  | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 3000 | 53000
| 6 | Reporting |  | RM | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 2100 | 37100
|  | 6.1 | Progress report |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6.2 | Achievement report |  | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 2100 | 37100
| 7 | Resource mobilisation |  | RM | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 900 | 15900
|  | 7.1 | Contribute to funding proposals |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 7.2 | Quarterly request for appropriation from FIN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 7.3 | Develop a donor pack of materials |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 7.4 | Promote GDF to the corporate sector selling the GDF in language they can understand |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 900 | 15900
| 8 | Internal management |  | RM | 0 | 0 | 0 | 0 | 63000 | 0 | 0 | 0 | 3780 | 66780
|  | 8.1 | Management of GDF resources, products and activities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8.2 | Biannual retreas to strategies on workplan |  | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 180 | 3180
|  | 8.3 | Staff meetings bi-weekly & monthly GMS meeting |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8.4 | Monitor all workwith WHO to ensure that it adheres to MOU close relevant to GDF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8.5 | Ensure all staff (including regional staff) trained in relevant competencies |  | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 3600 | 63600
|  | 8.6 | Implement PMDS for GDF staff. Secure 2 FT post for GDF P staff and 1 FT for G staff |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | Information management |  | TR | 0 | 0 | 49000 | 0 | 0 | 0 | 0 | 0 | 2940 | 51940
|  | 9.1 | Maintenance of ISO certificaiton status |  | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 300 | 5300
|  | 9.2 | Maintain and/or enhance GDF management system |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 900 | 15900
|  | 9.3 | Support finace/ work plan monittoring through GDF management system |  | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 180 | 3180
|  | 9.4 | Improve financial system |  | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 780 | 13780
|  | 9.5 | Regualarly calcualte and report on GDF spending and funding gap |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 9.6 | Evaluate remote access by regional staff to GDF management system |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 9.7 | Evaluate information needs of regional staffing and impact on GDF processes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 9.8 | Standerdize/automate data collection from TB technical units / systems |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 9.9 | Introduce enhanced , country focused public web presence and information delivery |  | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 780 | 13780
| 10 | GDF general management staff |  | RM | 894000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53640 | 947640
|  | 10.1 | Matiru Robert |  | 366000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21960 | 387960
|  | 10.2 | Ryan Timoty |  | 366000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21960 | 387960
|  | 10.3 | Karahasanovic Edin |  | 162000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9720 | 171720