| Summary Sheet |  |  |  |
| --- | --- | --- | --- |
| Agenda nr. 2.08-12.0 | Subject | TITLE: The Global Plan progress report, 2006-2008 |  |
| #### For information | #### For discussion X |  | #### For decision |
| Rationale: The Partnership Secretariat, the WHO Monitoring and Evaluation (TME) unit and the Working Groups are tasked with the monitoring and evaluation of the implementation of the Global Plan to Stop TB (2006-2015). The overall purpose of this project is to measure the implementation of the Global Plan activities for the period 2006-2008, in relation to the stated objective and milestones and generate a 3-year report to be released at the 2009 Partners Forum. |  |  |  |
| Summary: The review of progress in implementing the strategic plans of the Stop TB Working groups should inform any necessary adjustments in such plans. In addition, the report should aim to produce possible recommendations to improve the implementation of the overall Global Plan activities in areas falling behind. Terms of reference were prepared and circulated with the Coordinating Board. A Steering Committee has been also put together and a consultant hired to work with the Working Groups Chairs and Secretariat to compile the available data. Using the WHO Stop TB Department's TB database combined with input from the Secretariats of the WGs, a first draft of the report has been prepared. It is focusing on progress towards the major targets and related milestones set for the seven major components of TB control and research considered in the Global Plan i.e. DOTS expansion, MDR-TB, TB/HIV, ACSM, new diagnostics, new drugs and new vaccines. For DOTS expansion, MDR-TB, TB/HIV and ACSM, progress is being analysed both overall and for the seven epidemiological regions considered in the Global Plan, with progress (or lack of progress) highlighted for specific countries that drive regional trends. Preliminary results suggest that implementation and expansion of DOTS has exceeded most of the Global Plan estimates at the global level. Implementation of drug-resistant and TB/HIV collaborative activities is falling behind and major effort will be needed to ensure acceleration of drug resistance, TB/HIV control and ACSM activities. The research and development area of new TB tools is progressing but is still facing major challenges to achieve the 2015 targets. Among the 19 candidates in the pipeline, three new diagnostic tests have been endorsed by the Strategic and Advisory Group of WHO, and are currently being implementing in some selected countries. Regarding drug development, novel candidates have expanded the pipeline, and progress has been made in the field of clinical trials. There is some improvement in the number of vaccine candidates in the pipeline and in the pace at which new candidates have entered clinical trials. An assessment on financial investments in TB research and development will be available after the publication of the progress report. For each of these seven areas, the contribution of the Working Groups has been highlighted. The Secretariat would like to share provisional findings with Board members and to receive input and advice that will help to ensure a high-quality final report. |  |  |  |
| Decisions requested (from Stop TB Coordinating Board): - To provide guidance and feedback on the initial findings of the Global Plan Progress Report - To call on all Partnership bodies to provide the necessary data and inputs - To mandate publication of the progress report in time for the next Partners' forum |  |  |  |
| Implications (political / financial / staffing, etc): None |  |  |  |
| Next Steps |  |  |  |
| Action Required: Revision of the first draft of the progress report |  |  |  |
| Focal Point: Marcos Espinal, Katherine Floyd, Rachel Bauquerez and Timothy Ryan |  |  |  |
| Timeframe: To March 2009 |  |  |  |