## Sheet1
Schedule 1 2.08-14.2A
Stop TB Partnership Workplan Implementation as of 30 September 2008
No. | Area of Work (AoW) | RO | Planned cost | Budget | Encumbrance | Expenditure | Expenditure | Impl.rate vs Budget cost | Impl. rate vs. planned cost
1 | Country level ACSM | Young-Ae | 1225000 | 933516 | 108698 | 174626 | 283324 | 30.35% | 23.13%
2 | Global advocacy | LB | 2006000 | 1038249 | 44458 | 712201 | 756659 | 72.88% | 37.72%
3 | Global Fund proposal preparation and implementation | TB Team | 794000 | 794000 | 124971 | 485257 | 610228 | 76.85% | 76.85%
4 | TB Profile enhancement | Vittorio | 1290000 | 302783 | 65676 | 192448 | 258124 | 85.25% | 20.01%
5 | Global communication | Judith | 1000000 | 425872 | 71015 | 276850 | 347865 | 81.68% | 34.79%
6 | Governance |  | 1963760 | 369917 | 36397 | 184648 | 221045 | 59.76% | 11.26%
7 | Partnership building | Nelly | 2125840 | 779976 | 65976 | 355961 | 421937 | 54.1% | 19.85%
8 | Admin and financial mgt | AV | 712000 | 712000 | 120349 | 619638 | 712000 | 100% | 100%
9 | Support and innovation |  | 778000 | 196997 | 17620 | 49108 | 66728 | 33.87% | 8.577%
10 | Total Support to Working Groups (note 1) |  | 3400000 | 1211000 | 0 | 1211000 | 1211000 | 100% | 35.62%
| GRAND TOTAL |  | 15294600 | 6764310 | 655160 | 4261737 | 4888910 | 72.28% | 31.96%
Note:
1) Planned cost for Working Groups was initially US$7,280,000 (which makes total planned cost US$19,174,600 as per the initially approved WP in October). This figure was reduced to US$3,400,000 after consultation with the Executive Committee in December 2007.
0