## TB-HIV WG
IMPLEMENTATION WORKING GROUPS
TB/HIV WORKING GROUP
OBJECTIVES |  | ACTIVITES | PRODUCTS | INDICATORS | MILESTONES
[5 empty] | By end 2007 | By end 2010 | By end 2015
1 | To scale up and expand collaborative TB/HIV activities |  |  | Presence of an integrated national M&E system for collaborative TB/HIV activities that informs annual NTP planning cycles and their mid-term (3-5 years) plans.
1.1 | To scale up implementation of the TB/HIV policy |  |  |  | All high burden (Category 1) countries to have established national TB/HIV coordinating bodies and started implementing TB/HIV activities. | All Category 1 countries to have implemented recommended TB/HIV activities countrywide. | Full global implementation of TB/HIV activities as defined in TB/HIV policy.
[5 empty] | National TB/HIV coordinating bodies established in countries with administrative areas where HIV prevalence is greater than 1% (Category 2). | All Category 2 countries to have commenced scale up of TB/HIV activities in all administrative areas where HIV prevalence is greater than 1%.
Establishment of national HIV surveillance among TB patients in all Category 3 countries.
1.2 | To expand the scope of existing global policy to increase accessibility and acceptability of collaborative TB/HIV activities |  |  |  | - Global TB/HIV policy guidelines for women, IDU, prisons, children and mobile populations produced. - TB/HIV guidelines on infection control and intensified TB case finding produced. | - New TB/HIV policy and guidelines implemented in all high TB/HIV burden countries (Cat 1) - TB/HIV activities included in maternal and child health, harm reduction and prison health services in all high TB/HIV burden countries.
1.3 | To address immediate gaps and bottlenecks in the implementation of TB/HIV services. |  |  |  | - Updated guidelines on TB/ART co-treatment and improved diagnostic algorithms produced. - Training materials published
1.4 | To improve quality improvement through surveillance, monitoring and evaluation |  |  |  | - Annual global report on TB/HIV activities, focusing on the highest TB/HIV burden countries, to be produced as part of the WHO Global Tuberculosis Control Report. - All high TB/HIV burden countries to be reporting core TB/HIV indicators11 to WHO. - Develop practical toolkit for HIV surveillance in lower HIV prevalence settings. | All countries to be reporting data from HIV surveillance among TB patients to WHO. | All countries achieving the Partnership’s 2015 targets and the MDGs.
2 | To develop and coordinate implementation of research to improve the prevention, early diagnosis and rapid treatment of TB in PLWHA and incorporate results into global policy |  |  | Number of operational research developed at country level/include in national strategic plan | - All high TB/HIV burden countries to include operational research on TB/HIV activities in their national TB, TB/HIV and/or HIV strategic plans. - TB/HIV operational research planning and proposal development workshops conducted in all regions. - At least 10 high TB/HIV burden countries to conduct TB/HIV operational research activities according to the regional needs. | - Research planning and proposal development follow up meetings held in each region to present results - All high TB/HIV countries to establish TB/HIV OR programmes to inform national scale up of TB/HIV activities - TB/HIV research agenda adapted to reflect regional needs - New tools from Drugs, Diagnostics and Vaccines WG tested and implemented in high HIV settings.
2.1 | To continually refine the prioritized research agenda for collaborative TB/HIV activities and support operational research on TB/HIV at country level. |  |  |  | TB/HIV operational research planning and proposal development workshops conducted in all regions.
2.2 | To translate research findings into global policy and practice. |  |  |  | Annual TB/HIV WG meetings held either globally or regionally to disseminate research findings and best practice and to define policy needs. |  | DEWG goals achieved
3 | To increase political and resource commitment to collaborative TB/HIV activities. |  |  | National TB control policy, endorsement by government, adresses the link between TB and HIV, and the potential impact that HIV may have on TB control throughout the country
3.1 | To mobilize technical, financial, and human resources |  |  |  | - Resource needs for TB/HIV activities mapped for all high TB/HIV burden countries. - Resource mobilisation plans developed for all high TB/HIV burden countries - Forum on involvement of HIV organisations in TB/HIV activities held at global HIV/AIDS meeting | - All high TB/HIV burden countries have adequate financial resources for planned activities to 2015.
3.2 | To implement advocacy and communication |  |  |  | - Global advocacy and communication strategy for TB/HIV activities - Ensure that Stop TB Partnership high level missions address TB/HIV - TB/HIV to feature at high level political meetings in the high TB/HIV burden regions, e.g. regional Ministers of Finance and Heads of States meetings and meetings of regional political partnerships (African Union, NEPAD). | - TB/HIV activities included in TB and HIV work-plans of national ministries of health and development agendas of all high TB/HIV burden countries.
4 | To contribute to strengthening health systems to deliver collaborative TB/HIV activities. |  |  | Number of health care facilities and/or congregate settings with a written infection control policy for TB that is consistent with international guidelines.
4.1 | To strengthen DOTS-based TB control and comprehensive HIV/AIDS prevention, care and support. |  |  |  | - Intensified action plan for Africa (Blueprint /Roadmap) fully implemented. - DEWG goals achieved | - DEWG goals achieved - All eligible HIV positive TB patients have access to ART | DEWG goals achieved
4.2 | To develop a multisectoral approach to collaborative TB/HIV activities with strong programme planning, management and sustainable financing. |  |  |  | - Produce global guidelines on developing a multisectoral, partnership approach to TB/HIV. - Establish a regional Stop TB Partnership for Africa. - All Category 1 TB/HIV countries to o develop a national multisectoral partnership to address TB and TB/HIV, o include TB/HIV activities in annual and mid term plans of the Ministry of Health, o have a plan for financing TB/HIV activities to reach the 2015 targets. - HIV community representatives included in national and regional Stop TB partnerships. - TB community representative included in national and regional HIV/AIDS partnerships. | - Establish regional TB/HIV WGs in the regions with the highest burden of HIV related TB. - Sustainable financing plans for achieving the 2015 TB targets in all high burden TB/HIV countries - TB and TB/HIV included in national development plans of all high burden TB/HIV countries
4.3 | Human resource capacity development |  |  |  | - Annual TB/HIV consultant training courses in all regions. - Develop integrated training materials on TB and HIV for use in high TB/HIV burden countries. - All high burden TB/HIV countries to assess human resource requirements for health and develop a long term human resource for health development plan. - Technical assistance needs defined for implementing TB/HIV activities in the high burden TB/HIV countries - Attain levels of externally funded technical assistance staff at country and national level defined in the optimistic realistic scenario. | Attain levels of externally funded technical assistance staff at country and national level consistent with the intensified action approach. | All high TB/HIV burden countries to have adequate human resources for TB/HIV activities
4.4 | To engage all health care providers in collaborative TB/HIV activities. |  |  | Number of potential partners in collaborative TB/HIV activities who are actively involved in the planning, implementation and monitoring of collaborative TB/HIV activities, expressed as a proportion of all potential partners. | - Develop guidance on involvement of health providers outside the public health sector in TB/HIV activities. - Establish pilot projects on public/private and public/public mix for TB/HIV. | All high burden TB/HIV countries have plans for engaging all health providers in TB/HIV activities.
4.5 | To engage people with TB and HIV and affected communities in planning, delivering, monitoring and evaluating collaborative TB/HIV activities. |  |  |  | - Develop community mobilisation strategy for TB/HIV activities. - Hold activist training workshops once a year in the highest HIV burden regions. - Include TB/HIV activities in TB and HIV community mobilisation strategies in all high burden TB/HIV countries.
4.6 | To strengthen laboratory capacity for collaborative TB/HIV activities |  |  |  | - Comprehensive global laboratory strengthening strategy to support TB/HIV activities. - New diagnostic protocols to improve TB diagnosis among PLHIV, especially addressing smear negative TB using existing technologies. - Plan to expand access to rapid TB culture methods in the high TB/HIV burden countries. | Plan to test and implement new diagnostic tools in high TB/HIV prevalence countries.

## MDR-TB WG
IMPLEMENTATION WORKING GROUPS
MDR-TB WORKING GROUP
OBJECTIVES |  | ACTIVITIES | PRODUCTS | INDICATORS | MILESTONES
[5 empty] | By end of 2006 | By end of 2007 | By end of 2008 | By end of 2009 | By end of 2010 | By end of 2015
1 | To expand drug resistance surveillance |  |  |  | - Drug resistance data available from more than 110 countries for analysis and publication including data from additional areas of China, India and the Russian Federation, new data from high-burden countries including Bangladesh and Indonesia, and from new suspected high-MDR-TB burden countries including Ukraine and Kyrgyzstan. - Data available from three new priority settings (i.e. high MDR-TB or HIV settings) combining DRS and HIV surveillance among TB patients. | - Drug resistance data available from seven new countries with high TB burden, expected high MDR-TB prevalence or high HIV prevalence. - Data on the relationship between HIV and MDR-TB available from two new settings. - Data on trends in drug resistance available from three new settings. | - Drug resistance data available from seven new countries with high TB burden, expected high MDR-TB prevalence or high HIV prevalence. - Data on relationship between HIV and MDR-TB available from two new settings. - Data on trends in drug resistance available from five new settings. | - Drug resistance data available from ten new countries with high TB burden, expected high MDR-TB prevalence or high HIV prevalence. - Data on relationship between HIV and MDR-TB available from two new settings. - Data on trends in drug resistance available from seven new settings. | - Drug resistance data available from ten new settings with high TB burden, expected high MDR-TB prevalence or high HIV prevalence. Data from 130 countries ready for publication, with half of them reporting trend data with three or more data points. - Data on relationship between HIV and MDR-TB available from two new settings. - Revision of estimates on the global MDR-TB burden published. | - Drug resistance data available representing 90% of settings with expected high MDR-TB prevalence or high HIV prevalence settings. 70% of settings reporting trend data with three or more data points. Reliable trends available from key high MDR-TB and HIV prevalence settings. - Data on relationship between HIV and MDR-TB established. - Revision of estimates on the global MDR-TB burden published.
2 | To monitor trends and regularly update the global MDR-TB estimates |  |  |  | Laboratory assessments and proficiency testing of 20 new NRLs. | All countries with high MDR-TB prevalence and high TB burden having NRLs performing quality-assured culture and DST and collaborating with a supranational TB reference laboratory (SRL). |  |  | - All countries having NRLs performing quality-assured culture and DST and collaborating with an SRL. - DST expanded to cover 92% of all new and previously treated cases in eastern Europe. All other Regions performing DST to approximately 60% of targeted previously treated patients and the Latin American, Southeast Asia and Western Pacific Regions, also performing DST to at least 10% of targeted new cases. | - All countries having NRLs performing quality-assured culture and DST and collaborating with an SRL. - All Regions should provide DST for all previously treated TB patients. In the eastern European Region, DST will also be provided for all new cases and in the Latin American, Southeast Asia and Western Pacific Regions, DST should be provided for 20% of targeted new cases.
3 | To strenghten capacity to perform quality-assured culture and drug susceptibility testing |  |  |  | DOTS-Plus expansion in India and the Russian Federation and pilot projects established in six new countries including China and the high MDR-TB burden country Kazakhstan. | DOTS-Plus expansion in India and the Russian Federation and pilot projects established in six new countries including the high-burden countries Bangladesh, Myanmar, Tanzania and Viet Nam. | DOTS-Plus expansion in India, China and the Russian Federation and pilot projects established in six new countries including the high-burden countries Indonesia and Pakistan. |  | Between 40-70% of detected MDR-TB patients in all Regions should have access to adequate MDR-TB treatment according to WHO guidelines. | All detected MDR-TB patients to have access to adequate MDR-TB treatment according to WHO guidelines.
4 | To scale up MDR-TB treatment according to WHO guidelines |  |  |  | - Meetings conducted with second-line drug manufacturers in China, India and the Russian Federation in order to increase the number of manufacturers on the WHO white-list of prequalified second-line drugs. - The white-list of prequalified second-line drug manufacturers containing at least two manufacturing sources per drugs published. - An inventory of global second-line drug use published. - A buffer stock of second-line drugs created enabling the GLC to deliver drugs in a timely fashion. |  |  |  | Quality-assured production of second-line drugs in high-MDR-TB burden countries including China, India, the Russian Federation and South Africa. | Capacity building: all Regions and countries including DRS and MDR-TB management in regular TB courses and workshops.
5 | To create a healthy and competitive market of quality-assured second-line drugs |  |  |  | - The structure and functions of the Stop TB Working Group on DOTS-Plus for MDR-TB and its subgroups including the GLC reviewed and adapted to the new challenge of scaling-up the diagnosis and treatment of MDR-TB reaching beyond the initial phase of piloting MDR-TB management. DRS included in the Working Group. - All WHO Regions to have strategic plans for DRS and DOTS-Plus and two Regions to have developed regional GLCs. - Capacity building: two DOTS-Plus capacity building centres set-up in the Western Pacific Region, key NTP staff trained in DOTS-Plus from the countries of the former Soviet Union and from the WHO African, American, Southeast Asian and Western Pacific Regions. Training manual on DOTS-Plus developed and additional TB consultants trained in DOTS-Plus. - The new DOTS-Plus and the DRS guidelines printed and disseminated in Chinese and Russian. - Development of guidelines for DOTS-Plus management in the private sector and establishment of DOTS-Plus projects in additional private sector TB control programmes. -Sub-meeting of the Stop TB Working Group on DOTS-Plus for MDR-TB conducted. - Annual SNRL meeting held. - Finalization of the standardization of DST to second-line drugs. | - Meeting of the Stop TB Working Group on DOTS-Plus for MDR-TB conducted. - Annual SNRL meeting held. - DRS, MDR-TB management and second-line drug management built into general TB management courses. - Evaluation of feasibility, effectiveness and cost-effectiveness of standardized treatment approaches to MDR-TB control. | - All WHO Regions having regional GLC mechanisms reviewing applications and ensuring that DOTS-Plus is monitored regularly as part of routine TB control missions. - Sub-meeting of the Stop TB Working Group on DOTS-Plus for MDR-TB conducted. - Annual SNRL meeting held. | - Meeting of the Stop TB Working Group on DOTS-Plus for MDR-TB conducted. - Annual SNRL meeting held. | - Meeting of the Stop TB Working Group on DOTS-Plus for MDR-TB conducted. - Annual SNRL meeting held.
6 | To provide technical and global coordination to accomplish the goals |  |  |  | By 2006, the structure and functions of the Stop TB Working Group on DOTS-Plus for MDR-TB and its subgroups, including the GLC, will be reviewed and adapted to the new challenge of scaling up the diagnosis and treatment of MDRTB, reaching beyond the initial phase of pilot-testing MDR-TB management. Drug resistance surveillance will be included in the Working Group. |  | By 2008, all WHO regions will have regional GLC mechanisms reviewing applications and ensuring that DOTS-Plus is monitored regularly as part of routine TB control missions. By 2015, all regions and countries will include DRS and MDR-TB management in regular TB courses and workshops.

## DOTS Expansion WG
IMPLEMENTATION WORKING GROUPS
DOTS EXPANSION WORKING GROUP
OBJECTIFS |  | ACTIVITIES | PRODUCT | INDICATORS | MILESTONES
[5 empty] | 2010 | 2015
1 | To achieve and sustain performance beyong the "70/85" targets | Complete DOTS coverage |  |  | All public health basic management units in all countries will provide TB care according to the DOTS strategy by 2010
2 | To ensure equitable access to quality TB care for all people with TB, especially the poor and marginalized | Improvement quality of DOTS | Improve human resource capacity for DOTS needs including sputum smear microscopy, drug management, case management, supervision, recording and reporting and laboratory diagnosis. |  |  | All countries will provide quality diagnosis and treatment and achieve at least 85% treatment success rate
|  | Expand Public-Private mix DOTS |  |  | All countries will have developed guidelines for the involvement of relevant public and private health care providers in DOTS | 3.8 billion people will live in areas with PPM DOTS initiaves
|  | Increase the involvement of the DOTS Community | Decentralize TB services to increase geographical access and to foster people's participation in supporting patients. |  | All countries in Africa will have scaled up community DOTS initiatives | 1.9 billion people globally will live in areas with community DOTS initiatives
|  | Expand Practical Approach to Lung Health (PAL) | Improve the quality of care fro every respiratory patient and the efficiency of PHC services in treating respiratory conditions. |  | PAL will be introduced in 20 % of developing countries | PAL will be introduced in 50% of developing countries
|  | Develop capacity to perform culture services, drug succeptibility testing and new diagnostics tests | Improving performance of TB |  | From 2010, new diagnostic tools will be introduced gradually and are expected to cover at least 50% of the eligible population by 2015 | All countries will have the capacity to perform culture and DST according to national policies. New diagnostic tools are expected to cover at least 50% of the eligible population.
|  | Prioritize the needs of the poor and vulnerable | Increase the commitment of NTPs. Role of the TB and poverty working group. |  | All countries will have developed capacity to monitor the extent to which DOTS reaches and serves the poor and vulnerable.
[5 empty] | All countries will have developed key strategies for improving access to DOTS for the poor and vulnerable. | All countries will have developed the capacity to demonstrate and monitor the contribution made by DOTS to poverty alleviation.

## Drugs WG
RESEARCH WORKING GROUPS STRATEGIC PLANS
NEW TB DRUGS WORKING GROUP
| OBJECTIVES | ACTIVITIES | PRODUCTS | INDICATORS | MILESTONES
[5 empty] | 2010 | 2015
1 | Identify validated drug targets for pesistent bacilli and latent disease | Inclusion of related goals on TB drugs in the funding programs announced by major research funders (e.g., NIH, MRC, INSERM, European Commission,Wellcome Trust, etc.) |  | Number of candidate targets validated by molecular biology and animal experiments |  | Identify and validate drug targets for both persistent bacilli and latent disease
|  | Identification of novel drug targets and specific inhibitors |  | Number of research funders who have announced funding opportunities |  | Fully understand the mode of action of all compounds under development
|  | Clarification among academics and industry on the criteria by which drug targets can be considered validated |  | Number of relevant announcements offering at least $5 million in total awards |  | Determine the mechanisms of action of drugs in the global portfolio and then use this information to generate complementary or even synergistic combinaitions effective against the mycobacteria
|  | Publication of 10 validated drug targets |  | Number of relevant, validated bioassays available
Broad access for TB drug developers to validated bioassays, including high throughput screening, to identify new drug candidates in a timely fashion
2 | Ascertain mechanisms of action of drugs in the global portfolio to generate complementary or even synergistic combinations effective against M.tb. | Elucidate modes of action |  | Number of new drugs with mode of action identified | Introduction of a new drug combinaison of drugs that can reduce time of treatment to 3-4 months | To have a sustainaible portfolio of new drug candidates under development that meet the profile criteria required for the 1-2 month therapy
|  | Validate combinations |  | Confirmed laboratory data for effective new combination regimens in vitro and in vivo |  | Bring into clinical testing a rational combinaition drug therapy that can reduce the required treatment time to 1-2 months or less
Number of new mechanism-based regimens in at least 1 clinical trial
Number of new candidate targets for which at least 1 compound has entered preclinical testing
3 | Develop a sustainable portfolio of new drug candidates that meet the drug profile criteria. | A sustained pipeline of new drug candidates |  | Number of clinical trials evaluating shortened TB treatment regimens
|  | Introduction of a new drug or combination by 2010 |  | Number of candidates in discovery phase (e.g. 10 in lead identification stage)
|  | Development of rational combinations to reduce treatment to 1-2 months by 2015 |  | Published data supporting shortened treatment using in vitro and in vivo models
Number of drugs or formulations in development with once-daily dosing
Number of candidates with minimized side effects
Documented tolerance of candidate therapies in human volunteers
Number of candidate drugs with minimal effects of food on bioavailability
Number of candidates with no significant impact on cytochrome P450 isoenzyme activities, to help ensure compatibility with HIV/AIDS therapies
4 | Develop animal models that can predict compound activity and side effects, and validated surrogate markers that are broadly adopted by TB drug developers. | Development of a standard animal model that reliably predicts efficacy in humans |  | Animal models developed that reliably predict tolerability and efficacy and require shorter observation periods
|  | Development of 1 or more surrogate markers to give confidence of sterilization within 2 months |  | At least one surrogate marker shown to reliably predict outcome at 2 years
Percent reduction in length of required follow-up period
5 | Build clinical trial sites and initiate and conduct clinical trials that meet regulatory requirements and highest ethical standards. Develop biomarkers, surrogate endpoints and testing programs to speed future clinical development programs. | Within 5 years, develop sufficient clinical trial capacity to evaluate –evaluate 3 promising and complementary candidate drugs for treatment of active TB up to Phase III within 5 years –evaluate 2 promising candidate drugs for treatment of latent TB infection up to Phase III within 8 years –enroll up to 2,000 patients for each Phase III trial |  | Mapping project to identify trial sites and data centers with appropriate microbiology, staff and ICH 6 Good Clinical Practice guidelines in place
|  | Establish an effective 1-2 month regimen for the treatment of tuberculosis by 2015 |  | Expansion of global TB clinical trials enrollment capacity to 5,000 patients annually with active TB disease
|  | Establish a network of trial sites able to enrol at least 5,000 cases annually |  | Expansion of global TB clinical trials enrollment capacity to 5,000 patients annually with latent TB infection
|  | Ensure the timely registration of compounds |  | Outcomes in preclinical and early (Phase I and II) clinical trials for each drug tested
Number of sites with an annual incidence of new cases of greater than 200
Sites with laboratories capable of carrying out microscopy, culture and susceptibility tests and surrogates as they are developed
Sites with GCP and GLP international standards
6 | Establish harmonized regulatory guidelines, including fast-track approval for TB drug developers. | Approval of surrogate markers for conditional registration of TB therapies |  | Surrogate marker(s) of cure or efficacy approved by at least one developed country regulatory agency
|  | Expansion of global expertise in monitoring clinical trials |  | Number of agencies approving each proposed surrogate marker
|  | Registration of new drugs, singly and in combination |  | Number of drugs completing registration process
Number of entities with trained and funded clinical trial monitors

## Diagnostics WG
RESEARCH WORKING GROUPS STRATEGIC PLANS
NEW TB DIAGNOSTICS WORKING GROUP
| OBJECTIVES | ACTIVITIES | PRODUCTS | INDICATORS (apply to all 3 products) | MILESTONES
(apply to each objectif)
1 | (DISCOVERY) Address existing knowledge gaps obstructing development of new diagnostic tools | Sensitive, early detection of active disease | Discovery science to identify new markers (also in HIV-infected subjects) with improved discriminative power for active disease (may be antigenic, immunological, proteomic or other) | Number of studies received and financed through “Requests for Applications” | In 2005/2006, Select more promising antigen combinations based on available research data and expert knowledge and opinion (undertaken by FIND)
|  |  | Validation of candidate targets in suitable screening format (e.g. ELISA) with patient samples from target population(s) | Number of agencies having announced related funding opportunities | During 2006/2007, an improved POC test (for blood, serum, urine and saliva) will be developed
|  |  | Exploration and further refinement of understanding of transmission dynamics and natural history to inform mathematical modeling of potential impact of new diagnostic tools | Number of related peer-reviewed publications | Basic research will be needed for at least three or four more years until reasonable product devepment can be initiated
|  | Identification of LTBI at risk of progression | Discovery science to identify new markers (also in HIV-infected subjects) with improved discriminative power for predicting future progression to active disease (may be antigenic, immunological, proteomic or other) | Number of new promising technologies reported | During 2005 and 2006 FIND will assess the technical feasibility of several promising system concepts, in order to select development partner(s) which can develop a highly integrated NAAT product for use at the First referral level (district lab) or at the Peripheral Level (presently microscopy centre) until 2008
|  |  | Evaluation of predictive value in identifying subjects at risk of progression of next generation of existing tools for detection of LTBI | Number of new diagnostic reagents/targets identified
|  | Simple, rapid identification of drug resistance | Discovery science to identify novel markers of drug resistance for first and second line drugs in cultured isolate | Number of new promising technologies identified through landscape-mapping
|  |  | Discovery science to improve detection of drug resistance direct from patient samples | Number of requests for reference material received by sample and strain banks
|  |  | Validation of marker candidates in suitable screening format with patient samples from target population | Number of publications associated with use of sample and strain banks
Number of target validation studies performed under the auspice of the Diagnostic Working Group
Number of new targets with contractually assured affordable and sustainable product access
2 | (DEVELOPMENT) Development and evaluation of a portfolio of new diagnostic tools and demonstration of impact | Sensitive, early detection of active disease | Conceptualization and development initiation of simple rapid format tests for TB in sputum, serum, saliva or urine based on improved targets | Number of agencies announcing relevant funding opportunities | 2005/2006 - Rapid culture (+DST) at First Referral Level
| For all three indications: (below) ?? − Inclusion of related goals in research funding calls by major funding agencies − Public sector product development agreements with industry − Coordinated evaluation and demonstration projects |  | Introduction of least one product for the district laboratories by 2007 | Defined Customer Requirements and Product Specifications | 2006, improved microscopy at Peripheral lab
|  |  | Introduction of at least one product for the peripheral laboratories by 2008 | Number of Product Development agreements with industrial partners | 2007/2008, Phage detection (+DST) at First Referral level
|  |  | Introduction of at least one POC product for health centers by 2010 | Number of successfully completed Development and Technical Evaluations according to Product Specifications | 2008, Automated NAAT at First Referral Level
|  | Identification of LTBI at risk of progression | Conceptualization and development initiation of test for risk of disease progression in a suitable platform based on best candidates | Number of clinical evaluation and demonstration sites developed and authorized | 2008, Simplified NAAT at Peripheral Level
|  |  | Introduction of at least one product for point of care use by 2012 | Number of evaluation projects initiated | 2010, POC test for active disease at Point of Care Level
|  | Simple, rapid identification of drug resistance | Conceptualization and development initiation of tests for drug resistance requiring equal or less infrastructure and training than current technologies | Number of evaluation projects completed | 2012, Predictive LTBI at POC level
|  |  | Introduction of at least one product at first referral level by 2006 | Number of peer-reviewed publications reporting results from evaluation projects
|  |  | Introduction of at least one product at peripheral laboratory by 2008 | Agreement on empiric design of Demonstration studies with selected NTPs
Number of Demonstration Studies initiated
Number of Demonstration Studies completed
Number of peer-reviewed publications reporting results from Demonstration Studies
Number of new targets with contractually assured affordable and sustainable product access
3 | (ACCES) Implementation of new diagnostic tools and ensuring access | Definitive predictions of impact from the use of improved diagnostics on TB detection rate and transmission |  | Completion of mathematical model defining impact and cost-effectiveness
|  | Operational studies to demonstrate epidemiological and economic impact of new tools in high-burden settings |  | Number of countries with streamlined regulatory procedures for TB diagnostics
|  | Accelerated registration of products with proven utility |  | Number of market analysis updates
|  | National and international policy changes reflecting impact evidence on new diagnostics |  | Number of new diagnostic tools included in TB policy recommendations of international technical agencies
|  | • Creation of demand through communication to stakeholders (NTPs, MOH, technical and funding agencies.) |  | Number of new diagnostic tools included in national TB policy recommendations
|  | Ensured access to proven technologies through inclusion in GDF or other procurement mechanisms |  | Number of NTPs in which new diagnostic tools are implemented at district level
Number of NTPs in which new diagnostic tools are implemented at local level
Number of NTPs in which new diagnostic tools are implemented at point of care

## Vaccines WG
RESEARCH WORKING GROUPS STRATEGIC PLANS
WORKING GROUP ON NEW TB VACCINES
OBJECTIVES | ACTIVITIES | PRODUCTS | INDICATORS | MILESTONES
|  |  |  | 2006 | 2010 | 2015
Maintain and improve BCG vaccination programmes | Sustain BCG production by a diminishing number of international suppliers
Sustain BCG production by analysis of possible variations in vaccine efficacy as a result of genetic changes in BCG substrains
Establishment of a rational system for deciding when and how different substrains should be used.
Discovery and translation research ("kipping the pipeline filled)
Facilitate preclinical development | Development of facilities to product development pilot lots of vaccine candidates suitable for human trials
Ensure that these candidates are subject to appropriate tests to confirm biological potency and lack of toxicity in experimental systems
Build capacity at vaccines trial sites | Baseline epidemiological information
Development of community interaction programmes
Development of protocols that comply with legal and ethical requirements
Coordination with national authorities
Local proficiency in immunological assays and optimized diagnostics procedures
Infrastructure through the developmental vaccine will be delivered
Ensure availability of vaccine production capacity/scale-up | Distribution in multi-center and multinational studies which is essential for the selection candidates for clinical trials
New licensed vaccines will be available at a cost that is affordable for resource-poor countries
To respond to the demand, development of new innovative partnerships with manufacturers in developing and developed countries
Perfom clinical trials
Provide an enabling infrastructure
WORKING GROUP ON NEW TB VACCINES

## Partnership Secretariat
Stop TB Partnership - SECRETARIAT
OBJECTIVES |  | ACTIVITIES | PRODUCTS | INDICATORS | MILESTONES
[5 empty] | 2007 | 2009 | 2011 | 2015
1 | Promote accountability, flexibility and coordination in the management of partnership resources | To strengthen the Secretariat's reputation for accountable, flexible and well-coordinated management of resources. | [5 empty] | The Partnership Trust Fund should reach a cumulative US$500 million
2 | Stimulate the mobilization of the resources needed to permit the implementation of the Global Plan to Stop TB (2006-2015) | To mobilize the resources needed to enable the Partnership to fully implement the Global Plan to Stop TB (2006–2015). |  |  | 10% of GP funding requirements | 25% of GP funding requirements | 50% of GP funding requirements | 100% of GP fuding requirements
3 | Ensure the effective functioning, growth, dynamism and catalysing effect of the GDF in global TB control. | The GDF will provide a cumulative total of 25 million patient treatments through both grant and direct procurement service lines. |  |  | The supply of anti-TB drugs through the GDF will meet the biennial target of patient treatments to be delivered globally, as identified by the DOTS Expansion Working Group.
|  | Support for access to quality affordable anti-TB drugs will be provided in all countries where there is need. |  |  | The GDF will be prepared for the harmonized supply of TB/HIV preventive therapies by 2007 | The GDF will be prepared for possible TB/HIV treatment therapies
|  | The GDF will stimulate the development of viable markets for TB control products, other than first-line anti-TB drugs. |  |  | The longer-term aim is to support selfsufficiency in drug management at national and regional level through the implementation of the GDF’s Sustaining the Gains Strategy and the establishment of a technical assistance service line to broker support from partners for countries in need.
4 | Facilitate relationships between and with existing partners and strengthen our coalition by reaching out to new or potential partners | An increased number and proportion of TB stakeholders will become active partners in Stop TB. |  |  |  |  | 10 national partnerships will be established | 12 national partnerships will be established
5 | Build skills, resources and capacity at regional and national level to enable successful partnership to be developed | Skills and resources will be available at regional and national levels to develop successful Stop TB partnerships.
6 | Place TB on the global development agenda, while at the same time, mainstreaming pro-poor approaches into TB control | TB will be further mainstreamed into global and national development agendas.
Pro-poor approaches will be mainstreamed into TB control.
A unique brand for Stop TB will be accepted and promoted by all partners.
The Secretariat will organize at least three Partners’ Forum meetings during 2006–2015
7 | Take TB beyond the existing reach and scope of traditional disease control programme by catalizing new opportunities and promoting the aims and objectives of the Global Plan to Stop TB (2006-2015) | The Secretariat will be capable of supporting the retooling of partners, who require assistance, in preparation for the introduction of new products and new technologies. |  |  | TB will be further mainstreamed into the health systems strengthening agenda at global level and in important regional debates on development issues. A gender perspective and a human-rights-based approach will be integrated into all key Secretariat activity areas, including advocacy and communications, resource mobilization, partnership-building and technical assistance. | the Secretariat will facilitate a guide on the mainstreaming of human-rights-based approaches in TB programming | The Secretariat will secure strategic alliances to promote human rights, equity and gender awareness in global TB programming and Secretariat activities.
[6 empty] | The Secretariat will develop a network to broker technical assistance to retool the Secretariat and key partners and countries for the introduction of new technologies. |  | the Secretariat will have the skill set necessary to support the implementation of the next Global Plan to Stop TB.
8 | Monitor and evaluate the impact of the Secretariat and Partnership in delivery of the Global Plan to Stop TB (2006-2015) | Progress against the milestones, targets and impact of the Global Plan and working group activities will be evaluated and documented |  |  | The Secretariat will provide a progress report at each Partners’ Forum
[7 empty] | the Secretariat will facilitate a midterm review and progress report | The Secretariat will provide a final report on the Global Plan to Stop TB (2006–2015) and facilitate development of a further Global Plan for the next period.
WORKING GROUP ON NEW TB VACCINES

## ASCM WG Global level
ACSM WORKING GROUP at GLOBAL LEVEL
| ENTITY | OBJECTIVES | ACTIVITIES | PRODUCTS | INDICATORS | MILESTONES
[6 empty] | 2008 | 2010 | 2015
1 | Core | Meetings
Conference calls
2 | Secretariat | Website
Newsletters
Communications with TFs
|  | Communication with the Country level sub-group | Core Group conf calls
3 | Media and Events Task Force | Develop the Common Messaging Platform for TB
|  | Communications with other WGs | Improved information from WGs | Factsheets, messages and FAQs from all WGs
Identification of key technical speakers from WGs, WHO and Stop TB Partnership, editors and journalists
|  | Help to coordinate media activities around key events and strategic opportunities | IUATLD conference coverage Articles in newspapers, TV and radio
IAS conference coverage Articles in newspapers, TV and radio
WTBD coverage Articles in newspapers, TV and radio
World Aids Day Articles in newspapers, TV and radio
Use the influence of the media to build awareness, facilitate policy dialogue, advocate for policy and programmatic change and increased resources for TB
|  | Educate and engage the media in donor and endemic countries | Media training workshops with PANOS
Link national programmes to international media personalities and TB activities
|  | Provide a strong profile and voice for affected communities and assist social mobilization | Roster of speakers from key Stop TB Partnership civil society organizations in target countries
|  | Develop and maintain a database of key journalists | Develop a Roster of journalists
Develop a group of TB activists from the journalist community
Provide support to national programmes for media related activities
| Events | Develop a calendar of events | Update the calendar monthly
|  | Plan new events and opportunities that support the communications strategy and priorities for the Stop TB Campaign | New Events undertaken
Raise resources for the Media and Events Task Force
Quarterly progress reporting
2 | Business Engagement
3 | Building National Partnerships
4 | G8
5 | EU
6 | National Advocacy (Patient led)
7 | XDR-TB

## ACSM WG Country level
ACSM Working Group at Country Level
OBJECTIVES |  | ACTIVITIES | PRODUCTS | INDICATORS | MILESTONES
[5 empty] | 2008 | 2010 | 2015
1 | Build national and subnational ACSM capacity | All hight and medium-burden countries appoint national ACSM coordinator | Accelerate the production of a handbook for communication programming. Regular updates every two year. |  | At least 10 endemic countries will have developed and will be implementating multisectoral, participatory ACSM initiatives and generating qualitative and quantitative data on the contribution of the ACSM to TB control | At least 20 priority countries will be implementing multisectoral, participatory ACSM initiatives, and monitoring and evaluation their outcomes | Alll priority countries will be implementing effective and participatory ACSM initiatives
|  | All endemic countries carry out an ACSM needs assessment from which a 10-year ACSM stategy can be developed in partnership with other stakeholders | Use the assessment tool developed to assist country-level planning
Each country needs to have an agreed, prioritized, budgeted ACSM workplan and that budgets are specifically allocated for this work and explicitly built into GFATM proposals
Regurlar, structured meetings (at least every two months) need to happen with infected/affected communities and NTP programme
2 | Fostering inclusion of patients and affected communities | Creation of an environment that empowers patients and affected communities to participate effectively in programme design, implementation and monitoring | Methodologies and tools developed by patients to improve TB control programmes |  |  | Civil society TB advocacy organizations or coalitions will be functioning in 20 donor countries and 40 endemic countries | The ACSM WG will have helped to mobilize $56 billion for the control of TB and the development of new tools in accordance with the Partnership's Global Plan in order to achieve the MDG and meet the Stop TB Partnership's targets.
|  | Support for nurturing of TB and TB/HIV patient organizations and networks | Training programmes for patients to become community TB educators, monitors, and advocates
Capacity building for NTP staff at all levels in involving patients in TB programming
Development and advocacy of behavioural change strategies targeted at health workers to reduce stigma
Operational research to document good and innovative approaches that empower and involve patients and affected communities
Employement of patients representative in the Stop TB Secretariat to act as a focal point for action, support and representation
Active support strategies to enable patients/those most affected to participate effectively in programme design, implementation and monitoring
3 | Ensuring political commitment and accountability | Establishment of formal and informal national partnership composed of a broad coalition of stakeholders, including representatives from the affected/infected community, academic institutions, donors, private sectors, NGOs, media, etc. These partnerships should build upon the experiences and successes of existing national Stop Tb Partnerships | Formal and national partnership established
|  | The promotion of TB champions from both within government, specifically in parliament and the ministries of finance and health, and outside government (such as in the private sector). Promotion can take place through a range of activities including policy briefings, field visits, media events, programme reviews, etc. | Promote TB champions
4 | Forging country-level ACSM partnership within the context of NTPs
5 | Learning, adapting and building on good ACSM practises and knowledge exange
6 | GFATM
7
8